## SEO with GANTT Chart
Advanced SEO with GANTT Chart Planner |  |  |  |  | 0%
[5 empty] | 50% |  |  |  | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
100%
|  |  |  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | PERIODS
|  |  |  | START | DURATION | START | DURATION | COMPLETE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138
CH1 | INDEXATION & ACCESSIBILITY |  |  | 1 | 23 | 1 | 27 | 9.671%
1 | YOUR SITE LIKE A SEARCH ENGINE |  |  | 1 | 6 | 1 | 6 | 40%
|  | Install the Plugins |  | 1 | 8 | 1 | 6 | 100%
|  | Disable JavaScript in FireFox |  | 4 | 2 | 4 | 3 | 50%
|  | Disable CSS with the Web Developer Plugin |  | 4 | 3 | 4 | 6 | 50%
|  | Set User-Agent to Googlebot |  | 5 | 4 | 5 | 3 | 0%
|  | Fire up your website and browse! |  | 5 | 2 | 5 | 2 | 0%
2 | CRAWL YOUR SITE WITH SCREAMING FROG |  |  | 6 | 12 | 5 | 14 | 68.75%
|  | Crawl The Site |  | 6 | 1 | 5 | 8 | 100%
|  | Save Your Crawl |  | 9 | 3 | 9 | 3 | 100%
|  | Check Page Levels |  | 9 | 6 | 9 | 7 | 50%
|  | Check for Crawl Errors |  | 9 | 3 | 9 | 1 | 100%
|  | Find & Fix Long Titles |  | 9 | 4 | 8 | 5 | 50%
|  | Find & Fix Long Descriptions |  | 10 | 5 | 10 | 3 | 100%
|  | Look at Indexation Settings |  | 11 | 2 | 11 | 5 | 0% | bar: PERIODS 1
|  | How To Find All Pages With Any HTML |  | 12 | 6 | 12 | 7 | 50%
3 | SELF AUDIT FOR A SITE REDESIGN |  |  | 14 | 30 | 14 | 32 | 0%
|  | Create A Spreadsheet To Monitor Progress |  | 14 | 8 | 14 | 2 | 0%
|  | Monitor Number Of Pages Indexed |  | 14 | 7 | 14 | 3 | 0%
|  | Monitor Cache Date |  | 15 | 4 | 15 | 8 | 0%
|  | Monitor Pagerank |  | 15 | 5 | 15 | 3 | 0%
|  | Monitor Seomoz Domain Authority |  | 15 | 8 | 15 | 5 | 0%
|  | Monitor "Not Found" Errors |  | 16 | 28 | 16 | 30 | 0%
4 | TESTING A NEW SITE BEFORE IT GOES LIVE |  |  | 1 | 5 | 1 | 11 | 0%
|  | Get the IP address of your new website. |  | 1 | 6 | 1 | 6 | 0%
|  | Edit your hosts file to point to your IP address |  | 2 | 4 | 2 | 5 | 0%
|  | Test your website |  | 4 | 8 | 4 | 6 | 0%
|  | Undo Changes |  | 4 | 2 | 4 | 8 | 0%
5 | MIGRATING TO A NEW SITE WITHOUT DOWNTIME |  |  | 5 | 7 | 5 | 7 | 0%
|  | Set the TTL of your new domain to 5 minutes |  | 5 | 2 | 5 | 5 | 0%
|  | Locate the DNS settings for your domain |  | 5 | 2 | 5 | 6 | 0%
|  | Change the DNS settings on your current domain. |  | 18 | 12 | 8 | 15 | 0%
|  | Unset your hosts file by removing the lines you added in step #1. |  | 6 | 1 | 5 | 8 | 0%
|  | Wait 5 minutes, then try to go to your new website |  | 9 | 3 | 9 | 3 | 0%
6 | CRAWLABLE AJAX (USING JQUERY GET) |  |  | 9 | 12 | 8 | 9 | 0%
|  | Add a <DIV> tag with a unique ID in the body where your dynamic content will go |  | 9 | 4 | 8 | 5 | 0%
|  | Create your HTML template |  | 10 | 5 | 10 | 3 | 0% | bar: PERIODS 1
|  | Add jQuery to your site |  | 11 | 2 | 11 | 5 | 0%
|  | Add JavaScript to the site that will load content into the <DIV> tag |  | 12 | 6 | 12 | 7 | 0%
|  | Create your PHP script |  | 12 | 1 | 12 | 5 | 0%
|  | Test your script on your web server |  | 14 | 5 | 14 | 6 | 0%
|  | Check view-source |  | 14 | 8 | 14 | 2 | 0%
|  | Check Inspect Element |  | 14 | 7 | 14 | 3 | 0%
7 | CRAWLABLE AJAX (WITHOUT HASHES) |  |  | 15 | 7 | 1 | 36 | 0%
|  | Start by creating a PHP script that will add the proper <meta> tag in the header |  | 15 | 8 | 15 | 5 | 0%
|  | Next, we will create a function that renders the page |  | 16 | 10 | 16 | 10 | 0%
|  | Next, we will add code to handle the escaped fragment query string |  | 16 | 5 | 1 | 5 | 0%
|  | Next, we will create a content.php file |  | 15 | 6 | 1 | 6 | 0%
|  | Finally, we will create ajax_crawling.json |  | 17 | 4 | 2 | 5 | 0%
|  | Test the page as rendered by a user |  | 18 | 8 | 4 | 6 | 0%
|  | Look at the view source |  | 19 | 2 | 4 | 8 | 0%
|  | Look at the Inspect Elements view |  | 20 | 3 | 4 | 6 | 0%
|  | Check the bot's view by adding"?_escaped_fragment_" to the end of the URL |  | 20 | 4 | 5 | 3 | 0%
|  | Check view source of the bot's view |  | 20 | 2 | 5 | 32 | 0%
8 | CROSS DOMAIN REL=CANONICAL |  |  | 6 | 9 | 5 | 8 | 0%
|  | WHEN TO USE |  | 6 | 1 | 5 | 8 | 0%
|  | HOW TO IMPLEMENT |  | 9 | 3 | 9 | 3 | 0%
|  | LAST FEW HINTS |  | 9 | 6 | 8 | 5 | 0%
|  |  | Make the links absolute not relative (include the full http:// etc) | 9 | 3 | 9 | 1 | 0%
|  |  | Just like with 301s avoid chains of canonicals | 9 | 4 | 8 | 5 | 0%
|  |  | Ultimately this is a hint for Google, not an absolute direction, so you will want to check Google's index and webmaster tools to see if it has been followed. | 10 | 5 | 10 | 3 | 0%
9 | FIXING HTTPS DUPLICATE CONTENT ERRORS |  |  | 12 | 7 | 12 | 8 | 0%
|  | Finding https pages that have been indexed |  | 12 | 1 | 12 | 5 | 0%
|  | Diagnose Why They Ended Up In The Index |  | 14 | 5 | 14 | 6 | 0%
10 | PAGINATIONWITH REL=NEXT |  |  | 15 | 29 | 15 | 31 | 0%
|  | Identify Your Pages In The Series |  | 15 | 4 | 15 | 8 | 0%
|  | Add rel="next" To Page One |  | 15 | 5 | 15 | 3 | 0%
|  | Change the DNS settings on your current domain |  | 15 | 8 | 15 | 5 | 0% | bar: PERIODS 1
|  | Add rel="prev" to the last page |  | 16 | 28 | 16 | 30 | 0%
11 | REDIRECTING ERROR PAGES WITH .HTACCESS |  |  | 1 | 5 | 1 | 6 | 0%
|  | Create Your Error Page |  | 1 | 6 | 1 | 6 | 0%
|  | Configure .htaccess |  | 2 | 4 | 2 | 5 | 0%
0%
12 | OPTIMIZING RSS FEEDS |  |  | 4 | 2 | 4 | 8 | 0%
13 | VIDEO SITEMAPS |  |  | 5 | 7 | 5 | 9 | 0%
|  | Create an Empty XML File |  | 5 | 2 | 5 | 5 | 0%
|  | Paste This Into the XML File |  | 5 | 2 | 6 | 7 | 0%
|  | Submit Your Sitemap to Google Webmaster Tools |  | 6 | 6 | 5 | 9 | 0%
|  |  | Option ASubmit it to Webmaster Tools Directly | 6 | 1 | 5 | 8 | 0%
|  |  | Option BAdd The Following Line To Your Robots.txt File | 9 | 3 | 9 | 5 | 0%
0%
14 | .HTACCESS HACKS |  |  | 9 | 3 | 9 | 1 | 0%
15 | DETECTING GOOGLEBOT |  |  | 10 | 5 | 10 | 3 | 0%
16 | ADD CUSTOM SEARCH ENGINE TO YOUR SITE |  |  | 12 | 10 | 12 | 4 | 0%
|  | Compose a Title and Description |  | 12 | 1 | 12 | 5 | 0%
|  | Add Sites To Be Included in Search |  | 14 | 5 | 14 | 6 | 0%
|  | Select Edition and Confirm |  | 14 | 8 | 14 | 2 | 0%
17 | MULTILINGUAL MARKUPAND GOOGLE TRANSLATE |  |  | 1 | 5 | 1 | 11 | 0%
|  | PHASE I: GETTING THE CODE |  | 1 | 5 | 1 | 5 | 0% | bar: PERIODS 1
|  |  | Translate Page or Part of Page? | 15 | 8 | 15 | 5 | 0%
|  |  | Select Language of Your Webpage | 16 | 28 | 16 | 30 | 0%
|  |  | Show Optional Settings | 1 | 5 | 1 | 5 | 0%
|  | PHASE II: INSTALLING THE CODE ON YOUR SITE |  | 2 | 4 | 2 | 10 | 0%
|  |  | Decide Where You Want To Translate Box To Appear | 2 | 4 | 2 | 5 | 0%
|  |  | Installing The Code In The Header [option A] | 4 | 8 | 4 | 6 | 0%
|  |  | Installing the Code in a Sidebar. [option B] | 4 | 2 | 4 | 8 | 0%
0%
18 | BLOCK POTENTIALLY MALICIOUS OR HARMFUL LINKS TO YOUR SITE |  |  | 5 | 4 | 5 | 3 | 0%
19 | BROWSER PLUGINS FOR ON-SITE ANALYSIS |  |  | 19 | 5 | 20 | 8 | 75%
CH2 | SITE SPEED & PERFORMANCE |  |  | 1 | 6 | 1 | 9 | 3.125%
1 | MEASURING YOUR SITE SPEED |  |  | 9 | 9 | 8 | 11 | 0%
|  | Go To Google PageSpeed Online |  | 9 | 4 | 8 | 5 | 0%
|  | Run The Tool On |  | 10 | 5 | 10 | 3 | 0%
|  | Run the Tool On Inner Pages |  | 11 | 2 | 11 | 5 | 0%
|  | Test Your Site For MOBILE Site Speed |  | 12 | 6 | 12 | 7 | 0%
2 | TRACK PAGE LOAD IN ANALYTICS |  |  | 1 | 6 | 1 | 6 | 25%
|  | SETTING UP TRACKING IN WORDPRESS |  | 14 | 6 | 14 | 4 | 33.33%
|  |  | Install the Normal Tracking Code | 14 | 7 | 14 | 3 | 0%
|  |  | Set Sample Rate | 15 | 4 | 15 | 8 | 100%
|  |  | Check Source Code | 15 | 5 | 15 | 3 | 0%
|  | SETTING UP TRACKING IN NON WORDPRESS |  | 1 | 6 | 1 | 6 | 16.67%
|  |  | Locate Your Google Analytics | 16 | 28 | 16 | 30 | 0%
|  |  | Add Page Load Time Code | 1 | 5 | 1 | 5 | 50%
|  |  | Add Sample Rate Code | 1 | 6 | 1 | 6 | 0% | bar: PERIODS 1
3 | USING YAHOO'S YSLOW PLUGIN |  |  | 4 | 5 | 4 | 4 | 0%
|  | Install YSlow |  | 4 | 2 | 4 | 8 | 0%
|  | Open and Run YSlow |  | 4 | 3 | 4 | 6 | 0%
|  | Reading The Results |  | 5 | 4 | 5 | 3 | 0%
4 | FINDING LARGE IMAGES TO REDUCE |  |  | 6 | 7 | 5 | 11 | 0%
|  | GOOGLE IMAGE SEARCH |  | 6 | 7 | 5 | 8 | 0%
|  |  | Go To Google Image Search | 6 | 1 | 5 | 8 | 0%
|  |  | Do A Site Search | 9 | 3 | 9 | 3 | 0%
|  |  | Shut Off Safe Search | 9 | 6 | 9 | 7 | 0%
|  |  | Filter By Size | 9 | 3 | 9 | 1 | 0%
|  |  | Look at Results | 9 | 4 | 8 | 5 | 0%
|  | USE SCREAMINGFROG SEO SPIDER |  | 11 | 2 | 11 | 5 | 0%
|  |  | Crawl The Site | 11 | 2 | 11 | 5 | 0%
5 | GOOGLE CLOSURE TO OPTIMIZE FOR SPEED |  |  | 12 | 1 | 12 | 5 | 0%
6 | OPTIMIZING CSS AND JS FILES |  |  | 14 | 5 | 14 | 8 | 0%
|  | Download and Install Less Applications |  | 14 | 7 | 14 | 3 | 0%
|  | Open the Less Application |  | 15 | 4 | 15 | 8 | 0%
|  | Open the Folder Where your CSS Files are and Rename your CSS Files as ".less" |  | 15 | 5 | 15 | 3 | 0%
|  | Drag the folder with your LESS files into the Less application |  | 15 | 8 | 15 | 5 | 0%
|  | Click on Compiler, then Compile All |  | 16 | 2 | 16 | 2 | 0%
|  | Less will Automatically Minify your LESSFiles into CSS Files While it's Open |  | 14 | 5 | 17 | 5 | 0%
7 | INSTALLING GOOGLE'S MOD_SPEED FOR APACHE |  |  | 2 | 4 | 2 | 5 | 0%
8 | BROWSER CACHING(NON-WORDPRESS SITE) |  |  | 4 | 3 | 4 | 6 | 0%
|  | Log Into Your FTP Server and Backup Your .htaccess file |  | 4 | 3 | 4 | 6 | 0%
|  | Find Your .htaccess File |  | 5 | 4 | 5 | 3 | 0%
|  | Download and Backup the .htaccess File |  | 5 | 2 | 5 | 5 | 0%
CH3 | NEW SEARCH |  |  | 4 | 30 | 4 | 32 | 0%
1 | SCHEMA.ORG METADATA IMPLEMENTATION |  |  | 9 | 4 | 8 | 5 | 0%
|  | Basic Attributes Of Microdata |  | 9 | 3 | 9 | 1 | 0%
|  | Using Schema In Your Blog |  | 9 | 4 | 8 | 5 | 0%
2 | VIDEO INDEXATION MARKING UP YOUR VIDEOS WITH SCHEMA.ORG |  |  | 12 | 10 | 12 | 4 | 0%
|  | Paste the Normal Video Code On Your Page |  | 12 | 6 | 12 | 7 | 0%
|  | Wrap In Video Object |  | 12 | 1 | 12 | 5 | 0%
|  | Add Basic Markup |  | 14 | 5 | 14 | 6 | 0%
|  | Add Additional Markup |  | 14 | 8 | 14 | 2 | 0%
3 | YAHOO SEARCH MONKEY RDFA |  |  | 15 | 5 | 15 | 3 | 0%
|  | UNDERSTANDING IDENTIFIERS |  | 15 | 5 | 15 | 3 | 0%
4 | ADDING THE DUBLIN CORE TO YOUR SITE |  |  | 16 | 28 | 16 | 30 | 0%
5 | GOOGLE REL=AUTHOR TAG IMPLEMENTATION FOR MULTIPLE AUTHOR SITES |  |  | 4 | 26 | 4 | 19 | 0% | bar: PERIODS 1
|  | SIMPLE METHOD |  | 4 | 2 | 4 | 8 | 0%
|  |  | Link To The Individual Author Profile From Each Post | 4 | 8 | 4 | 6 | 0%
|  |  | Each Author Adds "Contributor" Link To Every Blog They Are a Guest Author On | 4 | 2 | 4 | 8 | 0%
|  | ADVANCED METHOD |  | 5 | 25 | 5 | 18 | 0%
|  |  | Link To The Individual Author Profile From Each Post | 5 | 4 | 5 | 3 | 0%
|  |  | Add rel= "author" Links From Blog Posts To Profile Page | 5 | 2 | 5 | 5 | 0%
|  |  | Add rel="me" From Bio Pages To Google Profile | 5 | 2 | 5 | 6 | 0%
|  |  | Click on Compiler, then Compile All | 18 | 12 | 8 | 15 | 0%
6 | GOOGLE REL=AUTHOR TAG IMPLEMENTATIONFOR SINGLE AUTHOR |  |  | 9 | 3 | 9 | 1 | 0%
|  | Add Rel=Author To Your Site |  | 9 | 6 | 9 | 7 | 0%
|  | Link Back To Your Site From Your Google Profile |  | 9 | 3 | 9 | 1 | 0%
7 | ENTITY SEARCH |  |  | 10 | 5 | 10 | 3 | 0%
8 | ADDING YOUR SITE TO ENTITY BASED SOURCES |  |  | 25 | 9 | 28 | 8 | 0%
CH4 | WORDPRESS |  |  | 1 | 17 | 1 | 18 | 0%
1 | ADVANCED INDEXATIONFOR WORDPRESS SITES (YOAST SEO) |  |  | 15 | 4 | 15 | 8 | 0%
2 | SECURING WORDPRESS |  |  | 15 | 8 | 15 | 5 | 0%
3 | MAKING WORDPRESSCOMMENT REPLY LINKS NOFOLLO |  |  | 1 | 5 | 1 | 5 | 0%
4 | INTERNAL LINKINGWITH SEO SMART LINKS |  |  | 4 | 2 | 4 | 8 | 0%
|  | Install The Plugin |  | 4 | 8 | 4 | 6 | 0%
|  | Configure |  | 4 | 2 | 4 | 8 | 0%
5 | GET RID OF DATE IN SERPS / WORDPRESS |  |  | 5 | 4 | 5 | 3 | 0%
6 | CREATING A CUSTOM WORDPRESS AUTHOR BIO PAGE |  |  | 6 | 6 | 5 | 5 | 0%
|  | File Setup |  | 18 | 12 | 8 | 15 | 0%
|  | Current Author Detection |  | 6 | 1 | 5 | 8 | 0%
|  | Rough Draft |  | 9 | 3 | 9 | 3 | 0%
|  | Variables |  | 9 | 6 | 9 | 7 | 0%
|  | Putting It Together |  | 9 | 3 | 9 | 1 | 0%
7 | USING WP-SUPER CACHE |  |  | 10 | 5 | 10 | 3 | 0%
8 | ADDING YOUR SITE TO ENTITY BASED SOURCES |  |  | 12 | 6 | 12 | 7 | 0%
CH5 | ADVANCED DATA RESEARCH |  |  | 4 | 19 | 4 | 18 | 0%
1 | INTRO TO IMPORT XML |  |  | 15 | 4 | 15 | 8 | 0%
2 | IMPORTXML — QUORA/TWITTER |  |  | 15 | 11 | 16 | 7 | 0%
|  | Find a Group or Topic |  | 16 | 28 | 16 | 30 | 0%
|  | Enter The Quora URL In Column A |  | 15 | 5 | 16 | 5 | 0%
|  | Create the importxml Function To Scrape Usernames |  | 16 | 6 | 18 | 6 | 0% | bar: PERIODS 1
|  | Create Full URLs |  | 17 | 4 | 17 | 5 | 0%
|  | Scrape For Twitter URLs |  | 18 | 8 | 17 | 6 | 0%
3 | SCRAPING UBERSUGGESTFOR KEYWORD IDEAS |  |  | 4 | 3 | 4 | 6 | 0%
4 | FINDING ANY HTML IN A LIST OF WEB PAGES |  |  | 5 | 2 | 5 | 15 | 0%
|  | Google Searches |  | 5 | 2 | 5 | 6 | 0%
|  | Scrape the URLs from the Google Results |  | 18 | 2 | 8 | 12 | 0%
|  | Filter the URLs through Screaming Frog |  | 6 | 1 | 5 | 15 | 0%
5 | USE CITATION FINDER TO FIND LINK OPPORTUNITIES |  |  | 9 | 6 | 9 | 7 | 0%
|  | SEARCH (WITHOUT A PROJECT) |  | 9 | 3 | 9 | 1 | 0%
6 | HARVESTING EMAIL ADDRESSES |  |  | 11 | 2 | 11 | 5 | 0%
|  | GATHER URLS |  | 11 | 2 | 11 | 5 | 0%
7 | SOCIAL LISTENING:ADVANCED LISTENINGTO TWITTER |  |  | 12 | 1 | 12 | 5 | 0%
8 | BROWSER PLUGINS |  |  | 14 | 8 | 14 | 2 | 0%
9 | USING A PROXY |  |  | 15 | 8 | 15 | 7 | 0%
|  | Go to http://www.rosinstrument.com/proxy/ |  | 15 | 5 | 15 | 3 | 0%
|  | Copy and paste proxies into Scrapebox to Test Them |  | 15 | 8 | 15 | 5 | 0%
|  | Return Good Proxies Back To Main List |  | 16 | 28 | 16 | 30 | 0%
|  | Copy Proxy Address Into Your Rank Checking Software |  | 18 | 5 | 17 | 5 | 0%
CH6 | KEYWORD RESEARCH |  |  | 4 | 19 | 4 | 16 | 0%
1 | BEYOND GOOGLEADWORDS KEYWORDRESEARCH |  |  | 4 | 3 | 4 | 6 | 0%
2 | USE SEARCH SUGGEST SCRAPERS FOR FAST KEYWORD IDEAS |  |  | 5 | 2 | 5 | 5 | 0%
3 | USE GOOGLE CORRELATE |  |  | 18 | 12 | 8 | 15 | 0%
4 | TRACKING INTERNALSITE SEARCH |  |  | 9 | 6 | 8 | 5 | 0%
|  | Check How Your Site Does a Site Search |  | 9 | 6 | 9 | 7 | 0%
|  | Set It Up in Analytics |  | 9 | 3 | 9 | 1 | 0%
|  | How To Use The Data |  | 9 | 4 | 8 | 5 | 0%
|  | Take Action |  | 10 | 5 | 10 | 3 | 0%
5 | SCRAPING SEARCH SUGGEST FROM THE COMMAND LINE |  |  | 12 | 10 | 12 | 4 | 0%
|  | Extract Initial JS File |  | 12 | 1 | 12 | 5 | 0%
|  | Create an .sh File |  | 14 | 5 | 14 | 6 | 0%
|  | Run The Code In Terminal (Mac) |  | 14 | 8 | 14 | 2 | 0%
6 | RUNNING YOUR OWN KEYWORD FREQUENCYANALYSIS |  |  | 15 | 8 | 15 | 5 | 0%
|  | Create your .sh Code |  | 15 | 5 | 15 | 3 | 0%
|  | Run the Script |  | 15 | 8 | 15 | 5 | 0%
CH7 | LINK BUILDING WITH CONTENT |  |  | 2 | 10 | 2 | 8 | 0%
1 | CREATE A "TOP" LISTAND GET LINKS |  |  | 2 | 4 | 2 | 5 | 0%
2 | BUILD LINKS WITH PDFS |  |  | 4 | 2 | 4 | 8 | 0%
3 | LINK BUILDING WITH IMAGES |  |  | 5 | 2 | 5 | 6 | 0%
|  | Collect and format your photos |  | 5 | 2 | 5 | 5 | 0%
|  | Find People Who Need Your Photos |  | 5 | 2 | 5 | 6 | 0%
4 | CREATE A 3D JAVASCRIPTPAGE OR MICROSITE WITH HTML5 AND CSS3 |  |  | 9 | 3 | 9 | 1 | 0%
|  | Download the Code |  | 9 | 3 | 9 | 3 | 0%
|  | Install on your Server |  | 9 | 6 | 9 | 7 | 0%
|  | Create Your Slideshow |  | 9 | 3 | 9 | 1 | 0%
CH8 | LINK BUILDING TECHNIQUES |  |  | 1 | 14 | 1 | 12 | 3.333%
1 | SUBMIT TO SITES WITH FOLLOWED LINKS |  |  | 12 | 1 | 12 | 5 | 0%
2 | CAPTURING LINKS FROM BRAND MENTIONS |  |  | 14 | 8 | 14 | 2 | 0%
3 | USING SCRAPEBOXFOR FAST WHITE HATBLOG COMMENTING |  |  | 15 | 5 | 15 | 3 | 0%
|  | Open Text Files |  | 15 | 5 | 15 | 3 | 0%
4 | GETTING A LINK FROM DMOZ |  |  | 16 | 28 | 16 | 30 | 0%
5 | COMMENT LINKSWITH DISQUIS |  |  | 1 | 5 | 1 | 5 | 0%
6 | BROKEN LINK BUILDING |  |  | 4 | 3 | 4 | 7 | 0%
|  | Get Your Elements Ready |  | 4 | 8 | 4 | 6 | 0%
|  | Determine Google Queries |  | 4 | 2 | 4 | 8 | 0%
|  | Extract URLs |  | 4 | 3 | 4 | 6 | 0%
|  | Run URLs Through Screaming Frog (or Xenu Link Sleuth) |  | 5 | 4 | 5 | 3 | 0%
|  | Examine The URLs With Broken Links For Relevance |  | 5 | 2 | 5 | 5 | 0%
|  | Determine Google Queries |  | 5 | 2 | 5 | 6 | 0%
7 | ADDING EASY TO COPY AND PASTE EMBED CODE |  |  | 9 | 6 | 8 | 5 | 0%
|  | Switch To HTML Mode |  | 9 | 3 | 9 | 3 | 0%
|  | Display Image on Page |  | 9 | 6 | 9 | 7 | 0%
|  | Return Good Proxies Back To Main List |  | 9 | 3 | 9 | 1 | 0%
|  | Place The Contents Within <textarea> |  | 9 | 4 | 8 | 5 | 0%
|  | Preview The Page |  | 10 | 5 | 10 | 3 | 0%
8 | LINK BUILDING WITH YOUR TWITTER PROFILE |  |  | 12 | 6 | 12 | 7 | 0%
9 | COPY AND PASTING LINK BUILDING WITH TYNT |  |  | 14 | 5 | 14 | 6 | 0%
10 | FINDING AN INCREDIBLY LINK WORTHY DOMAIN |  |  | 15 | 29 | 15 | 31 | 0%
|  | Collect Some Words |  | 15 | 4 | 15 | 8 | 0%
|  | Use Bustaname to check for domains |  | 15 | 5 | 15 | 3 | 0%
|  | Use the Domain Maker |  | 15 | 8 | 15 | 5 | 0%
|  | Cross Check Social w/ Knowem |  | 16 | 28 | 16 | 30 | 0%
11 | RECOVERING LOST LINKS |  |  | 1 | 5 | 1 | 5 | 0%
12 | SECOND LEVEL LINK BUILDING |  |  | 4 | 3 | 4 | 6 | 0%
|  | Identify The Page On Your Site |  | 4 | 8 | 4 | 6 | 0%
|  | Identify High Converting Referrals |  | 4 | 2 | 4 | 8 | 0%
|  | How Does The Referring Page Rank? |  | 4 | 3 | 4 | 6 | 0%
13 | SECOND LEVELLINK PROSPECTING |  |  | 5 | 2 | 5 | 8 | 0%
|  | Fine tune some Google Searches |  | 5 | 2 | 5 | 6 | 0%
|  | Using the SERPs redux bookmarklet, pull the top ten results into a text file. |  | 18 | 12 | 8 | 15 | 0%
|  | Crawl the 10 URLs with Screaming Frog |  | 6 | 1 | 5 | 8 | 0%
14 | PERFORM A BACK LINK AUDIT |  |  | 9 | 6 | 9 | 7 | 50%
|  | Collecting Your Link Data |  | 9 | 3 | 9 | 1 | 0%
15 | SCALABLE OUTREACH |  |  | 10 | 5 | 10 | 3 | 0%
CH9 | SEARCH VERTICALS |  |  | 1 | 90 | 1 | 134 | 0%
1 | MOBILE FRIENDLYSITES — CSS |  |  | 14 | 5 | 14 | 9 | 0%
|  | Create Code To Detect The User Agent |  | 14 | 7 | 14 | 3 | 0%
|  | Create a Unique Mobile CSS File |  | 15 | 4 | 15 | 8 | 0%
2 | OPTIMIZING ONLINE SLIDESHOWS |  |  | 15 | 8 | 15 | 5 | 0%
3 | DRIVE TRAFFIC TO YOUR SITE WITH YOUTUBE |  |  | 1 | 6 | 1 | 9 | 0%
|  | Make Several Accounts |  | 1 | 6 | 1 | 6 | 0% | bar: PERIODS 1
|  | Make 3-4 Videos |  | 2 | 4 | 2 | 5 | 0%
|  | Alter The Videos Slightly(1 For Each Account) |  | 4 | 8 | 4 | 6 | 0%
|  | Upload |  | 4 | 2 | 4 | 8 | 0%
|  | Include Your Referral Link |  | 4 | 3 | 4 | 6 | 0%
|  | Increase View Count Early |  | 5 | 4 | 5 | 3 | 0%
|  | Other Youtube Ranking Factors |  | 5 | 2 | 5 | 5 | 0%
4 | LOCAL SEARCHTECHNIQUES |  |  | 18 | 12 | 8 | 15 | 0%
5 | INSTALLING THE FACEBOOK OPEN GRAPH |  |  | 9 | 9 | 8 | 11 | 0%
|  | Create A Facebook App ID |  | 9 | 6 | 9 | 7 | 0%
|  | Get The Like Button Code |  | 9 | 3 | 9 | 1 | 0%
|  | Get The Open Graph Tags |  | 9 | 4 | 8 | 5 | 0%
|  | Integrate The Like Button Code |  | 10 | 5 | 10 | 3 | 0%
|  | Integrate The Open Graph Code |  | 11 | 2 | 11 | 5 | 0%
|  | Test and Debug Your Open Graph Installation |  | 12 | 6 | 12 | 7 | 0%
6 | CREATE CLICK TO TWEETS |  |  | 14 | 5 | 14 | 9 | 0%
|  | Have Your Content Ready |  | 14 | 8 | 14 | 2 | 0%
|  | Use Click To Tweet To Create Your Link |  | 14 | 7 | 14 | 3 | 0%
|  | Add Your Links In the Content |  | 15 | 4 | 15 | 8 | 0%
7 | DETECTING IF USERS ARE LOGGED INTO SOCIAL NETWORKS |  |  | 16 | 36 | 16 | 38 | 0%
|  | Add Code To Header |  | 16 | 28 | 16 | 30 | 0%
|  | HTML To Display If Logged In Or Not |  | 20 | 25 | 20 | 26 | 0%
|  | Add Your Links In the Content |  | 22 | 30 | 23 | 31 | 0% | bar: PERIODS 1
8 | INSTALLING GOOGLEPLUS BADGES |  |  | 4 | 87 | 4 | 131 | 0%
|  | Find Your Google Profile ID |  | 4 | 2 | 4 | 8 | 0%
|  | Go To the Badge Profile Config Tool |  | 4 | 3 | 4 | 6 | 0%
|  | Enter Your Profile ID and Get The Code |  | 5 | 4 | 5 | 3 | 0%
|  | Add the Code To Your Site |  | 89 | 2 | 90 | 45 | 0%
Enter plan details in cells with white background only