## Work Breakdown Structure (WBS)
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | MFS Development Project | [6 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | Project Lead : Shahab Al Yamin Chawdhury | [6 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. |  |  | Project Start Date: |  | 2020-04-01
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. |  |  | Scrolling Increment: |  | 60 |  |  | May | [6 empty] | June | [27 empty] | July
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | Project Manager : TBA | time axis 2020-05-31 to 2020-07-25
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart. | NB : Press 1 or 2 to expand or collaps the data from the left corner
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Category | Assigned To | Progress | Start | No. Days | Column1 | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Subsidiary Company Formation | On Track | Project Director | 85% | 2020-06-01 | 70
| Board resolution for DFS subsidiary formation under PSO/PSP license | Milestone |  | 100% | 2020-03-12 | 20
| Bangladesh Bank approval along with PSO/ PSP license | High Risk |  | 0% | 2020-06-01 | 20
| MoA & AoA draft |  |  | 100% | 2020-03-12 | 20
| MoA & AoA finalization |  |  | 100% | 2020-03-12 | 20
| Registration of subsidiary under RJSC |  |  | 100% | 2020-03-12 | 20
| Trade license from Dhaka North City Corporation |  |  | 100% | 2020-06-01 | 30
| VAT Registration |  |  | 100% | 2020-06-01 | 30
| eTIN/ BIN Registration |  |  | 100% | 2020-06-01 | 30
| Deposit Paid up capital |  |  | 100% | 2020-03-12 | 20
| Organogram approval by board/ management |  |  | 100% | 2020-03-12 | 20
| Creating Company Bank Account |  |  | 100% | 2020-03-12 | 20
| On boarding of tier-1/ HoD level |  |  | 90% | 2020-06-01 | 45
| Legal vetting of business scope |  |  | 0% | 2020-04-01 | 30
| Business Plan & Strategy Development: CyberSecurity/SOC | On Track | Ziaur Rahman | 80% | 2020-06-15 | 56
| Phase wise product priority setting submission |  |  | 100% | 2020-06-16 | 15
| Phase wise product priority setting approval |  |  | 100% | 2020-06-22 | 7
| Strategy workshop for business plan |  |  | 100% | 2020-06-20 | 7
| Respective function to submit their plan |  |  | 70% | 2020-06-23 | 2
| Final Business plan & Strategy submission to the Project Director |  |  | 0% | 2020-07-30 | 6
| Final Business plan & Strategy submission to the board |  |  | 0% | 2020-08-07 | 15
| Business plan (along with top line strategy) approval by the board |  |  | 0% | 2020-08-25 | 7
| Business Process readiness & sign-off | On Track | PM |  | 2020-07-05 | 60
| 1.SCM Process |  | Akram | 100% | 2020-07-05 | 10
| 2. Distributor on boarding process |  | Nasir | 100% | 2020-07-05 | 15
| 3.Agent on boarding process |  | Nasir | 100% | 2020-07-05 | 35
| 4. Merchant onboarding process |  | Rezwanul | 100% | 2020-07-05 | 60
| 5.Customer acquisition/registration process |  | Nasir |  | 2020-07-05 | 24
| 6.Customer Bulk registration process |  | Nazim | 100% | 2020-07-05 | 15
| 7. AML CFT process (Anti-Money Laundering & Countering the Financing of Terrorism Process) |  | to be |  | 2020-07-05 | 24
| 8. Lifting & refund process |  | Nasir |  | 2020-07-05 | 15
| 9. Commission disbursement process |  | Nasir |  | 2020-07-05 | 15
| 10. Customer complain handling process |  | Jesan |  | 2020-07-05 | 18
| 11. Complain (fraud/ LEA related) handling process |  | Mahbubur |  | 2020-07-05 | 24
| 12. HR Process |  |  |  | 2020-07-05 | 24
| 13. FDoA (Financial Delegation of Authority) |  | Siddiquee |  | 2020-07-05 | 24
| Critical Resource onboarding & HR Mgt | On Track | Ahmed Pasha | 80% | 2020-06-01 | 100
| Develop recruitment and employee on boarding process |  |  | 100% | 2020-06-10 | 15
| Organogram approval by board/ management |  |  | 100% | 2020-07-01 | 21
| Recruitment requisition preparation and mgt. approval |  |  | 100% | 2020-07-09 | 7
| Headcount and budget forecast sharing with management |  |  | 100% | 2020-07-12 | 7
| Draft HR Policy & Guidelines (manual) submission |  |  | 0% | 2020-07-21 | 45
| Defining all job role |  |  | 0% | 2020-07-15 | 60
| KPI Define & approval from the management |  |  | 0% | 2020-07-15 | 60
| Recruitment interview & selection for tier-1, 2,3 |  |  | 90% | 2020-07-01 | 60
| Laptop/desktop /others requisition to IT |  |  | 90% | 2020-07-01 | 60
| On boarding of tier-1, 2, 3 |  |  | 80% | 2020-07-01 | 75
| Existing resource reallocation | On Track |  | 100% | 2020-07-01 | 40
| Budget approval (Soft launch) | On Track |  | 100% | 2020-07-01 | 30
Technology
| Technology : Technology Architecture Planning & Deployment | On Track | Tech Head | 30% | 2020-07-10 | 21
| Technology planning & system |  | Shahab | 100% | 2020-04-10 | 7
| Tech system detail plan and budget submission |  | Shahab | 100% | 2020-04-10 | 5
| Tech system detail plan and budget approval | On Track | Project Director |  | 2020-07-15 | 5
| Aggregator integration_ITCL |  | BackEnd |  | 2020-09-15 | 5
| Bank API Integration |  | BackEnd |  | 2020-10-15 | 5
| Payment Gateway API Integration |  | BackEnd |  | 2020-10-15
| e-Commerce Platform API Integration |  | BackEnd |  | 2020-10-15
| International Remittance Services API Integration |  | BackEnd |  | 2020-10-15
| Bill Payment Merchant API Integrations |  | BackEnd |  | 2020-10-15
| Value Added Service Merchant API Integration |  | BackEnd |  | 2020-10-15
| Integration with Google mapping |  | BackEnd |  | 2020-10-15
| Integration with NPSB for other banks fund transfer (Add money) |  | Arch |  | 2020-10-15
| Recruitment requisition to HR |  | Tech Head |  | 2020-04-10
| Recruitment interview for tier-3 |  | Tech Head |  | 2020-06-01
| Final selection and appointment letter issue of tier-3 |  | Tech Head |  | 2020-06-01
| On boarding of tier-3 |  | Tech Head |  | 2020-07-01
| Recruitment interview for tier-2 |  | Tech Head | 80% | 2020-06-01
| Final selection and appointment of tier-2 |  | Tech Head |  | 2020-06-01
| On boarding of tier-2 |  | Tech Head |  | 2020-07-01
| Recruitment interview for tier-1 |  | Tech Head | 50% | 2020-08-01
| Final selection and appointment of tier-1 |  | Tech Head |  | 2020-08-16
| On boarding of tier-1 |  | Tech Head |  | 2020-10-01
| Team KPI submission |  | Tech Head |  | 2020-08-01
| Team KPI management approval |  | PD |  | 2020-09-01
| DFS Platform Development | On Track | Tech Head |  | 2020-07-12 | 110
| DFS platform requirment compilation - SRS Pending |  | Business |  | 2020-07-15 | 20
| Functional Business requirement collection from relevant stakeholders |  | Business
| Functional Business requirement draft submission |  | Business
| Functional Business requirement signoff |  | Project director
| Prepare SRS (Software requirement Specification) |  | Manik/Business Team
| SRS signoff |  | Project Director
| Detail project roadmap submission |  | Shahab | 100%
| Hardware & associated 5 yrs infra installation |  | Shahab | 100%
| DR site & Replica installation plan |  | Shahab | 100%
| MNO connectivity establishment |  | Nazim
| 3rd party integration |  | BackEnd
| UCASH Existing DB data migration |  | BackEnd
| UCASH USSD Module Integration/Migration |  | BackEnd
| UPAY Existing DB data migration |  | BackEnd
| Phase-1 deployment activity finish |  | BackEnd
| Phase-1 UAT |  | BackEnd
| Phase-1Testing& Bug fixing |  | BackEnd
| Platform handover to DFS team |  | BackEnd
| Platform live with phase-1 requirment |  | BackEnd
App Development
| Application Platform Architecture Design Plan | On Track | Shahab |  | 2020-07-15 | 78
(1) Customer App Workshop
Customer app requirement compilation
Customer app requirement finalization (functional & UI UX) & Signoff
Customer app development RFQ float with the vendors
Customer app, Vendor proposal submission
Technical evaluation of vendors and short listing
Commercial negotiation with vendor
Customer app vendor management approval
Customer app vendor PO issue
Customer app development kick off
Customer app UI/UX development and management review
Customer app final UI/UX development and management approval
Customer app Beta release
Customer app UAT
Customer app bug fixing
App Terms & Conditions development
App Terms & Conditions legal vetting
Customer app final release in app store (Android version)
Customer app final release in app store (iOS version)
Agent app Project team formation & Charter signoff
Agent app requirement compilation
Agent app requirement finalization (functional & UI UX) & Signoff
(2) Agent app development RFQ float with the vendors
Agent app, Vendor proposal submission
Technical evaluation of vendors and short listing
Commercial negotiation with vendor
Agent app vendor management approval
Agent app vendor PO issue
Agent app development kick off
Agent app UI/UX development and management review
Agent app final UI/UX development and management approval
Agent app bug fixing
Agent app Beta release
Agent app UAT
Agent app final release in app store (Android version)
DSO app project team formation and project charter signoff
(3) DSO App Requirement Compilation
DSO app requirement finalization (functional SRS & UI/UX) & Signoff
Distribution management system (DMS) development
Distribution management system (DMS) live
DSO app development RFQ float with the vendors
DSO app, Vendor proposal submission
Technical evaluation of vendors and short listing
Commercial negotiation with vendor
DSO app vendor management approval
DSO app vendor PO issue
DSO app SRS UI/UX development and management review
DSO app SRS final UI/UX development and management approval
DSO app development kick off
DSO app bug fixing
DSO app Beta release
DSO app UAT
DSO app final release in app store (Android version)
(4) Merchant app requirement compilation
Merchant app requirement finalization (functional SRS & UI/UX) & Signoff
Merchant app development RFQ float with the vendors
Merchant app, Vendor proposal submission
Technical evaluation of vendors and short listing
Commercial negotiation with vendor
Merchant app vendor management approval
Merchant app vendor PO issue
Merchant app SRS UI/UX development and management review
Merchant app SRS final UI/UX development and management approval
Merchant app development kick off
Merchant app bug fixing
Merchant app Beta release
Merchant app UAT
| Merchant app final release in app store (Android version) |  |  |  | 2020-10-01
To be add more milestone
| Key Service & Hardware Procurement & WH buildup (SCM) | On Track | Akram |  | 2020-06-01 | 120
| Procurement | On Track |  | 71% | 2020-06-10 | 90
| Procurement Process Development and submission |  |  | 100% | 2020-06-10 | 15
| Procurement Policy Development and submission |  |  | 100% | 2020-06-20 | 10
| Procurement policy & process management approval |  |  | 50% | 2020-06-20 | 10
| Team role definition and job profile |  |  | 100% | 2020-06-20 | 10
| On boarding of Procurement team |  |  | 60% | 2020-07-20 | 30
| Prepare & get approved BoQ for Tech Hardware purchase |  |  | 100% | 2020-06-01 | 60
| Purchase Tech Hardware for launch critical |  |  | 80% | 2020-06-01 | 90
| Prepare list of service/Product to prucure by discussing stakeholders |  |  | 0% | 2020-08-01 | 10
| Purchase launch critical Product & service |  |  | 50% | 2020-09-01 | 30
| Logistics & Warehousing | On Track | Akram |  | 2020-07-01 | 90
| Warehouse location sourcing |  |  | 100% | 2020-06-10 | 15
| Warehouse location management approval |  |  | 100% | 2020-06-20 | 10
| Transport/ courier service sourcing |  |  | 0% | 2020-06-20 | 10
| Transport/ courier service vendor management approval |  |  | 0% | 2020-06-20 | 10
| Logistics/warehouse management SOP submission |  |  | 100% | 2020-06-20 | 10
| Logistics/warehouse management SOP sign off |  |  | 0% | 2020-06-20 | 10
| Team role definition and job profile |  |  | 100% | 2020-08-16 | 15
| Recruitment requisition to HR |  |  | 100% | 2020-08-16 | 15
| On boarding of warehouse employee |  |  | 0% | 2020-08-16 | 15
| Warehouse policy & process prepardness & mgt approval |  |  | 100% | 2020-08-16 | 15
| Channel commission structure finalization | On Track | Biplab Banerjee |  | 2020-08-01 | 30
| Channel commission structure Prepare & approved |  |  | 80% | 2020-08-01 | 30
| Business Operation ( onboarding of distributor, agent, retailer) | On Track | Biplab Banerjee | 21.11% | 2020-06-01 | 120
| Sales_distribution (Channel readiness) |  |  |  |  | 0
| Channel strategy and roll out roadmap development |  |  | 100% | 2020-06-10 | 28
| Acquisition strategy development and submission |  |  | 100% | 2020-06-15 | 9
| Transaction & Cash management strategy development and submission |  |  | 20% | 2020-06-20 | 10
| Strategy review by management and approval |  |  | 50% | 2020-06-25 | 10
| Team structure finalization |  |  | 100% | 2020-06-15 | 5
| Team role definition and job profile |  |  | 100% | 2020-06-15 | 10
| Recruitment requisition to HR |  |  | 100% | 2020-06-25 | 5
| Recruitment interview done |  |  | 70% | 2020-06-15 | 22
| Final selection and appointment of tier 1 |  |  | 100% | 2020-07-20 | 30
| Distributor appointment criteria & process submission |  |  | 100% | 2020-06-15 | 9
| Distributor appointment process management approval |  |  | 0% | 2020-06-24 | 10
| Retailier appointment criteria & process submission |  |  | 100% | 2020-06-15 | 9
| Retailier appointment process management approval |  |  |  | 2020-06-24 | 10
| Geographic demarkation preparation with mapping (Region/ Area/Territory) |  |  | 100% | 2020-07-03 | 7
| Screening & review of existing channel partners |  |  | 0% | 2020-07-15 | 20
| Territory wise potential distributors document collection |  |  | 10% | 2020-08-01 | 90
| Channel partner/ distributor screening |  |  |  | 2020-08-07 | 90
| Channel partner/ distributor short-listing |  |  |  | 2020-08-15 | 90
| Channel partner/ distributor appointment finish |  |  |  | 2020-11-15 | 1
| Distributor Field force on boarding |  |  |  | 2020-10-01 | 120
| Team KPI submission |  |  |  | 2020-07-20 | 7
| Team KPI management approval |  |  |  | 2020-07-25 | 5
| Sales Operation | On Track | Biplab Banerjee |  | 2020-04-10 | 129
| Distribution agreement draft preparation |  | Nasir | 100% | 2020-07-20 | 10
| Distribution agreement draft vetting |  | Nasir | 0% | 2020-07-26 | 5
| Distribution agreement draft_managment approval |  | Project Director | 0% | 2020-08-01 | 4
| All documents of distributor archieved |  | Nasir |  | 2020-08-01 | 90
| Entry of distributor data in the system |  | Nasir |  | 2020-08-15 | 60
| Distributors live in the system |  | Nasir |  | 2020-10-01 | 20
| Distributor's Bank A/C opening activity |  | Nasir |  | 2020-09-15 | 20
| Distributor's Banking information integration with company |  | Nasir |  | 2020-09-15 | 25
| Distribution SOP submission |  | Nasir |  | 2020-07-20 | 30
| Distribution SOP management approval |  | Project Director |  | 2020-08-20 | 5
| Cash management process management approval |  | Nasir | 90% | 2020-07-25 | 5
| Portal uses guideline (user manual) & arrange a training |  | Nasir |  | 2020-10-01 | 15
| Portal user access creation for distributors |  | Nasir |  | 2020-10-07 | 20
| Portal uses guideline (user manual) & arrange a training |  | Akram |  | 2020-07-15 | 16
| Field force monitoring app training |  | Nasir |  | 2020-08-14 | 17
| Field force monitoring app rollout |  | Nasir |  | 2020-09-15 | 15
| Develop forecast for KYC requirement |  | Nasir |  | 2020-09-15 | 15
| Channel Development & Commissioning | On Track | Head of Sales | 0% | 2020-08-07 | 97 | 97
| Alternate channel strategy & plan submission |  | Head of Sales |  | 2020-08-07 | 7 | 7
| Alternate channel strategy & plan approval |  | Head of Sales |  | 2020-08-10 | 3 | 3
| Start sourcing for International Remittance partners |  | Head of Sales |  | 2020-08-07 | 7 | 7
| Agreement signing International Remittance partners |  | Head of Sales |  | 2020-04-10 | 15 | 15
| Payment & Merchant | On Track | Nurul H Manik | 40% | 2020-05-05 | 130
Merchant Ecosystem development
| Payment and merchant strategy and plan submission |  |  | 50% | 2020-06-05
| Payment and merchant strategy and plan management approval |  |  |  | 2020-06-20 | 14
| Merchant acquisition and closure process submission |  |  | 50% | 2020-05-05 | 50
| Merchant acquisition and closure process signoff |  |  | 30% | 2020-06-16 | 30
| Team role definition and job profile |  |  |  | 2020-07-01 | 14
| On boarding of Merchant tier 1, 2, 3 |  |  |  | 2020-09-01 | 29
| Team KPI submission |  |  |  | 2020-08-07 | 7
| Team KPI management approval |  |  |  | 2020-08-16 | 15
| Merchant KYC field finalization (Standard, e-KYC other) |  |  |  | 2020-07-01 | 14
| Merchant KYC design draft |  |  |  | 2020-07-15 | 16
| Merchant KYC legal vetting |  |  |  | 2020-07-31 | 7
| Merchant KYC design finalization/ management apporval |  |  |  | 2020-08-07 | 7
| Merchant operation manual (for all merchant segments) draft submission |  |  |  | 2020-06-30 | 82
| Merchant operation manual management review & sign off |  |  |  | 2020-08-01 | 13
| Merchant branding/merchandizing plan submission |  |  |  | 2020-08-14 | 17
| Merchant branding/merchandizing plan approval |  |  |  | 2020-09-01 | 14
| Merchant communication/ campaign plan for awareness |  |  |  | 2020-08-01 | 13
| Enterprise Sales Channel ( B2B, G2B) | On Track | Zahid |  | 2020-07-01 | 60
| Enterprise business strategy & roadmap development (Corporate,SME, Govt.) |  |  |  | 2020-07-01 | 15
| Enterprise business strategy & roadmap management review and approval |  |  |  | 2020-07-16 | 7
| Team structure finalization |  |  |  | 2020-07-01 | 15
| Team role definition and job profile |  |  |  | 2020-07-15 | 7
| Onboarding of Enterprise sales force |  |  |  | 2020-08-01 | 30
| Team KPI submission |  |  |  | 2020-08-01 | 7
| Team KPI management approval |  |  |  | 2020-08-07 | 7
| Product Development & Pricing | On Track | Head of Strategy | 0% | 2020-06-01 | 70
| Need gap scoping & opportunity mapping |  | Saajid | 100% | 2020-07-01 | 1
| Segment specific B2C product roadmap(with proposition) plan submission |  | Saajid |  | 2020-07-02 | 3
| Product design finalization and share with Finance |  | Saajid |  | 2020-07-07 | 7
| Segment specific B2B product roadmap submission(collection/disbursement) |  | Saajid |  | 2020-07-10 | 3
| Product design finalization and share with Finance |  |  |  | 2020-07-15 | 7
| Segment specific B2B product roadmap management apporval |  | Saajid |  | 2020-07-21 | 7
| Channel Charges & Commission management submission |  |  |  | 2020-07-22 | 15
| Channel Charges & Commission management approval |  |  |  | 2020-08-07 | 5
| Merchant Charges & Commission submission |  |  |  | 2020-06-15 | 15
| Merchant Charges & Commission management approval |  |  |  | 2020-08-07 | 7
| Product configuration in the System |  |  |  |  | 0
| Customer Charges/ Pricing configuration in the System |  |  |  |  | 0
| Channel Charges & Commission configuration in the System |  |  |  |  | 0
| Agreement review, renewal & contract sign | On Track | Ziaur | 20% | 2020-06-01 | 122
| Prepare list of existing contracts & prioritize the criticality |  | Rezwanul | 100% | 2020-06-01 | 7
| kick off renewal & new contract negotiation process |  | Rezwanul | 100% | 2020-06-07 | 7
| USSD agreement review/renewal with GP, Robi & banglalink |  | Saajid | 100% | 2020-10-01 | 0
| USSD agreement signing with Teletalk |  | Saajid |  | 2020-08-07 | 55
| USSD connectivity establishment with Teletalk |  | Saajid |  | 2020-10-01 | 0
| SMS agreement review/renewal with GP, Robi & banglalink |  | Saajid |  | 2020-07-15 | 78
| SMS connectivity establishment with Teletalk |  | Saajid |  | 2020-09-25 | 5
| Top-up Agreement with all |  | Saajid |  | 2020-06-01 | 122
| Top-up Connecivity with all |  | Saajid |  | 2020-06-25 | 98
| Agreement with EC- NID Server |  | Akram |  | 2020-07-20 | 73
| Connectivity with EC- NID Server |  | Akram |  | 2020-07-30 | 63
| Agrement with payment vendors: Visa, Master, UnionPay |  | Mani |  | 2020-07-01 | 92
| Integration with Visa, Master, Union Pay, Amex |  | Manik |  | 2020-08-01 | 61
| Agreement with banks for cash management |  | Majid |  | 2020-08-01 | 61
| Brand & Market Communication | On Track | Head of Brand | 0% | 2020-07-07 | 60
| Brand development |  | Head of Brand
| Brand development workshop |  | Nuzhat | 100% | 2020-07-07 | 38
| Brand workshop presentation to management |  | Nuzhat | 100% | 2020-08-14 | 6
| Brand logo submission |  | Nuzhat | 100% | 2020-07-16 | 29
| Brand logo review & approval by management |  | Project Director |  | 2020-08-07 | 7
| Brand logo architecture & elements/ Logo guideline submission |  | Nuzhat |  | 2020-08-15 | 16
| Brand essence, value, positioning submission |  | Nuzhat |  | 2020-08-15 | 16
| Vision & Mission submission |  | Nuzhat |  | 2020-08-15 | 16
| Brand imagery, layout, look and fill, Tone of voice |  | Nuzhat |  | 2020-09-01 | 14
| Visual guideline submission |  | Nuzhat |  | 2020-09-01 | 14
| Brand guideline 1st draft submission |  | Nuzhat |  | 2020-09-01 | 14
| Brand guideline 1st draft review |  | Nuzhat |  | 2020-09-01 | 14
| Brand guideline final submission |  | Nuzhat |  | 2020-09-15 | 7
| Brand guideline final review and sign off |  | Project Director |  | 2020-09-22 | 8
| Brand strategic framework |  | Nuzhat |  | 2020-09-01 | 14
| Phase by phase brand development plan |  | Nuzhat |  | 2020-08-15 | 16
| Brand copyright application |  | Nuzhat |  | 2020-08-15 | 16
| Creative & Production | On Track | Head of Brand |  | 2020-08-14 | 45
| Brief sharing to creative agencies for pitch |  | Nuzhat |  | 2020-08-14 | 4
| Creative agency pitch |  | Nuzhat |  | 2020-09-01 | 9
| Creative agency shortlist and negotiation |  | Nuzhat |  | 2020-09-01 | 9
| Creative agency awarding management approval |  | Project Director |  | 2020-09-10 | 10
| Creative agency agreement signing |  | Nuzhat |  | 2020-09-20 | 10
| Creative agency on board |  | Nuzhat |  | 2020-10-01 | 6
| Media | On Track | Head of Brand |  | 2020-08-07 | 22
| Media agency brief for pitch |  | Jesan |  | 2020-08-07 | 8
| Media agency pitch |  | Jesan |  | 2020-08-14 | 8
| Media agency shortlist and negotiation |  | Jesan |  | 2020-08-14 | 9
| Media agency awarding management approval |  | Jesan |  | 2020-08-23 | 8
| Media agency agreement signing |  | Jesan |  | 2020-09-01 | 6
| Media agency on board |  | Jesan |  | 2020-09-01 | 6
| Digital marketing | On Track | Head of Digital |  | 2020-08-07 | 52
| Digital marketing agency brief for pitch |  |  |  | 2020-08-07 | 8
| Digital marketing agency pitch |  |  |  | 2020-08-14 | 8
| Digital marketing agency shortlist and negotiation |  |  |  | 2020-08-14 | 9
| Digital marketing agency awarding management approval |  |  |  | 2020-08-23 | 8
| Digital marketing agency agreement signing |  |  |  | 2020-09-01 | 6
| Digital marketing agency on board |  |  |  | 2020-09-01 | 6
| Digital Marketing Strategy & Topline plan development |  |  |  | 2020-09-07 | 7
| Digital Marketing Strategy & Topline plan apporval |  |  |  | 2020-09-14 | 16
| Soft launch Campaign brief to digital marketing agency |  |  |  | 2020-09-07 | 7
| Digital marketing plan submission for soft launch |  |  |  | 2020-09-15 | 7
| Review and approval of digital marketing plan for soft launch |  |  |  | 2020-09-15 | 7
| Work order to digital marketing agency for soft launch |  |  |  | 2020-09-22 | 8
| Soft launch execution in digital space |  |  |  | 2020-10-01 | 29
| Social networking_Facebook page launch |  |  |  | 2020-10-01 | 29
| Social networking Linkedin page launch |  |  |  | 2020-10-01 | 29
| Social networking_Twitter page launch |  |  |  | 2020-10-01 | 29
| Social networking_Instagram page launch |  |  |  | 2020-10-01 | 29
| Promotion through Social media |  |  |  | 2020-10-01 | 29
| Promotion through Google (GDN) |  |  |  | 2020-10-01 | 29
| Market Communication for Soft launch |  | Head of Brand
| Draft launch plan for soft launch submission |  |  |  | 2020-08-14 | 17
| Campaign brief to creative agency |  |  |  | 2020-08-07 | 7
| Draft campaign proposal from creative agency |  |  |  | 2020-08-14 | 17
| Trade POSM design for launch- draft submission |  |  |  | 2020-09-01 | 13
| Trade POSM design for launch- Review & mgt. approval |  |  |  | 2020-09-14 | 8
| Trade POSM design for launch- final output delivery |  |  |  | 2020-09-22 | 8
| Agent communication material design |  |  |  | 2020-04-10 | 15
| Website | On Track | Head of Brand | 0% | 2020-08-01 | 150
| Website requirement collection for stakeholder |  | Wasi | 100% | 2020-08-01 | 6
| Website requirement sign off |  | Wasi | 50% | 2020-08-07 | 5
| Meeting with potential vendors |  |  |  | 2020-08-07 | 7
| RFQ for website |  |  |  | 2020-08-14 | 17
| Proposal submission by vendors for website |  |  |  | 2020-08-14 | 17
| Budget approval for Website |  |  |  | 2020-09-01 | 6
| PO issue for website |  |  |  | 2020-09-01 | 6
| Website domain purchase |  | Tech/SCM |  | 2020-09-07 | 7
| Website hosting plan finalization |  | Tech/SCM |  | 2020-09-14 | 16
| Website english content collection and sharing with the vendor |  | Head of digital |  | 2020-09-14 | 16
| Website images/ graphic elements sharing with the vendor |  | Head of digital |  | 2020-09-14 | 16
| Website development -Beta version |  | Vendor |  | 2020-09-15 | 30
| Website on air for soft launch |  | Vendor |  | 2020-10-15 | 7
| Website security certification |  | Tech |  | 2020-09-15 | 30
| Website development - Final version |  | Vendor |  | 2020-11-01 | 45
| Website on air_Final version (commercial) |  | Vendor |  | 2020-12-16 | 15
| Internal Communication | On Track | Brand Manager |  | 2020-08-14 | 50
| Internal communication plan submission |  |  |  | 2020-08-14 | 17
| Internal communication plan approval |  |  |  | 2020-09-01 | 6
| Internal communication activity for soft launch execution |  |  |  | 2020-10-01 | 21
| Call Center Readiness | On Track | Raisul | 5% | 2020-07-15 | 60
Call Centre
| Call Center Requirement Finalization |  |  | 100% | 2020-07-15 | 9
| RFP/ RFQ For Call Center |  |  | 100% | 2020-07-25 | 13
| Technical Evaluation |  |  | 100% | 2020-08-07 | 7
| Vendor Evaluation |  |  |  | 2020-08-07 | 7
| Call Center Vendor Finalization & approval |  |  |  | 2020-08-07 | 7
| Call Center Vendor PO issue |  |  |  | 2020-08-15 | 7
| Call Center Vendor agreement signing |  |  |  | 2020-08-15 | 7
| Call Center Agent on boarding |  |  |  | 2020-09-01 | 6
| Call Center Agent Training |  |  |  | 2020-09-01 | 6
| Call centre UAT |  |  |  | 2020-09-07 | 8
| Going Live |  |  |  | 2020-09-15 | 16
| Call centre agent for retailer and merchant |  |  |  | 2020-09-15 | 16
| Digital customer service interface activation |  |  |  | 2020-09-15 | 16
KYC & Customer data management
| KYC management process submission |  |  |  | 2020-08-07 | 8
| KYC management process sign off |  |  |  | 2020-08-15 | 7
| KYC archiving vendor sourcing |  |  |  | 2020-08-07 | 8
| KYC archiving vendor negotation and management approval |  |  |  | 2020-08-15 | 7
| KYC archiving vendor PO issue |  |  |  | 2020-09-22 | 8
| KYC vendor on boarding |  |  |  | 2020-09-01 | 14
| KYC physical archiving |  |  |  | 2020-09-15 | 16
| Initiate PR & external communication | On Track |  | 0% | 2020-08-01 | 60
| RFP/ RFQ For PR Agency |  |  |  | 2020-08-10
| Review Proposal / Agency Pitch |  |  |  | 2020-08-20
| Shortlist Agency & Negotiation |  |  |  | 2020-08-20
| Management Approval |  |  |  | 2020-08-20
| PR agency agreement |  |  |  | 2020-08-20
| PR Strategy & Plan submission |  |  |  | 2020-08-20
| PR Strategy & Plan approval |  |  |  | 2020-09-16
| PR activity for kick off |  |  |  | 2020-09-16
| Top tier Electronic media visit |  |  |  | 2020-09-16
| Top tier Print media visit |  |  |  | 2020-09-16
| Top tier Online media visit |  |  |  | 2020-09-16
| CEO's interview in Electronic media |  |  |  | 2020-09-16
| CEO's interview in Print media |  |  |  | 2020-09-16
| CEO's interview in online news portal |  |  |  | 2020-09-16
| Soft Launch preparation | On Track | Project Manager | 0% | 2020-09-01 | 31 | 75
| Launch plan (list of activity finalize) |  | Project Manager |  |  |  | 0
| Launch modality finalization |  | Project Director |  | 2020-09-01 | 1 | 15
| Launch campaign plan 1st draft submission |  | Project team |  | 2020-09-10 | 5 | 3
| Launch campaign plan management review |  | Project Director |  | 2020-09-15 | 5 | 7
| Launch campaign plan finalization/ management apporval |  | Project Director |  | 2020-09-20 | 5 | 5
| Launch budget approval |  | Project Director |  | 2020-09-20 | 7 | 6
| Soft Launch |  | Project Director |  | 2020-10-01 | 1 | 7
7
This is an empty row
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | To add more data, Insert new rows ABOVE this one