## Project Charter
Project Charter: Establish new datacenter and move existing datacenter devices to the new one
General Project Information
Project Name |  | Datacenter Migration | Extra Notes:
Project Sponsor
Project Manager
Email Address
Phone Number
Organizational Unit |  | PMO
Process Impacted |  | Datacenter functionality & operation
Expected Start Date |  | 1st of January 2022
Expected Completion Date |  | 11th of December 2022
Expected Savings (if any) |  | N/A
Estimated Costs (BDT) |  | 3410000
Green Belts Assigned |  | N/A
Black Belts Assigned |  | N/A
Describe the Problem or Issue, Goals, Objectives, and Deliverables of this Project
Problem or Issue | Performance information related to the current datacenter is not reliable and accurate as reported in the discussion group. This information is extracted from the Project Management System. Processes are poorly defined, inconsistent, and prone to high error rates each month. 2 incidents were recorded of high severity, which led us to source for an identical service provider, as an ISP, an NTTN with IGW & ICX, back-haul connectivity, MNO connectivity etc. to colocate our platform
Purpose of Project | This project will attempt to identify root causes behind distortions with actual project cost data in the Project Management System and implement solutions to fix broken processes in capturing and reporting business losses accordingly, while finalizing a new datacenter and relocate the complete platform
Business Case | Critical business decisions regarding IT investments depend upon reliable and accurate cost information. The current process needs upgradation and there are material distortions to the reporting of actual costs for IT projects within the Project Management System. This project will attempt to fix this broken process and give management the correct information needed for properly managing multi-million dollar investments in information technology for a future readiness in a Tier-III datacenter. The main benefit of this project has to do with improving the integrity of critical business application, data and the corresponding decision making processes surrounding this data, such as the Monthly Performance Reports.
Goals / Metrics | Design and develop a complete set of solutions to address root causes behind the impairment of actual cost data in the Project Management System for the uncontrolled downtime of the platform, placed in the current datacenter. At the highest level, this involves two data streams: Timesheets for Labor Costs and Expense Entries for all other costs. Determine the causes behind timesheets not processed and / or processed incorrectly. Determine the causes behind expense entries not processed and / or processed incorrectly. Determine the full extent of the problem through data analysis, interviews, and other tests regarding the current datacenter establishment. Develop solutions for improving all the application and network processes and monitor the results of the implemented solutions with the CISO staff.
Expected Deliverables | Project Charter, Stakeholder Analysis, Thought Process Map, Critical to Quality Characteristics, Pareto Chart of Errors in Cost Data, Attribute Measurement System Analysis on the platform, Baseline DPMO / Sigma Levels, Root Cause Analysis, Hypothesis Testing, Statistical Process Control Charts, Proposed Solutions, Pilot Tests, Solutions Rating Matrix, Error Proofing, Improvement Implementation Plan, Control Plans, Standard Operating Procedures, Training Modules, and Project Summary Close Out
Define the Project Scope and Schedule
Within Scope | This project is limited to only the project that are considered "developmental" since these projects must report Earned Value Management and these projects currently rely on the Project Management System for cost data. NOC team will devise the transformation & movement checklist to transfer OLD-DC devices to the new DC
Outside of Scope | Projects not using the Project Management System will not be reviewed. Additionally, this project will not develop detail system requirements for the Project Management System. The focus will be on the process itself and how the process relates to source systems for data.
Tentative Schedule |  | Key Milestone | Start |  | Complete
|  | Form Project Team / Preliminary Review / Scope | 2021-12-01 |  | 2023-01-01
|  | Finalize Project Plan / Charter / Kick Off |  |  | 2023-01-01
Define Phase
Measurement Phase
Analysis Phase
Improvement Phase
Control Phase
Project Summary Report and Close Out
Define the Project Resources and Costs
Project Team |  | Shahab Al Yamin Chawdhury. In addition to the five core team members, System Administrative support & deliverables is understood for the life cycle of the project.
Support Resources |  | Project Management Office staff will provide some administrative help. Projects that are reviewed may get tasked to help with data gathering and collection, HW movement etc.
Special Needs |  | At least two of the core team members will need network access to the Project Management System (KAM Lutfullah & SK Faisal). The project will also need programming support to extract data from two other systems: All NMS and AppPlat NMS for IS Configuration & Verification.
Cost Type |  | Vendor / Labor Names | Rate-BDT | Qty | Amount-BDT
Labor |  | Vendor Name - TBA | 50000 | 1 | 50000
Colocation Addition (Monthly recurring chargeable items) |  | Rack (2) Power (2) Internet (40mbps) | 220000 | 12 | 2640000
3rd Party Channel Movement |  | 3rd Party channel availability without having more than 3 HOP (source><DC><destination) |  | 0 | 0
HW & SW Configuration |  | In House - NOC Team, Dev Team |  | 0 | 0
Logistics |  | In House - Admin Team |  | 0 | 0
VA/PT |  | In House - CSOC Team |  | 0 | 0
Partner Support |  | Relevant partners for HW |  | 0 | 0
Sanitization |  | In House - NOC Team |  | 0 | 0
Fooding & Hotel Cost |  | Support for In-house team members | 60000 | 12 | 720000
|  |  | Total Cost |  | 3410000
Define the Project Benefits and Customers
Process Owner |  | Md. Hafizullah (CTO) owns the overall process over this movement reporting for IT Hardware movement to the new DC. Each Project Manager must make sure they follow a set of procedures for capturing and reporting actual costs correctly. The Project Management Office provides oversight and support for the processes and completion reporting of activities.
Key Stakeholders |  | All personnel assigned to IT Developmental Projects, including Project Managers, Project Analyst, Project Planners, Project Schedulers, and Budget Managers. All personnel who provide leadership support above the project level, including the Chief Information Security Officer, the CISO Staff, Directors and Senior Managers within the IT Department and outside departments or agencies that have an interest in the cost performance of IT investments within the agency.
Final Customer |  | Chief Information Security Officer and Chief Technology Officer
Expected Benefits |  | Less variations and inconsistencies in how all projects currently report actual costs. Fewer material distortions between the resources actually used by the project vs. what gets reported as actual costs incurred.
Tasks |  | Descriptions |  |  | Percentile
Power |  | Consistency of sustainable power and precision air conditioners |  |  | 99
Internet |  | Network & internet availability |  |  | 99.99
Channel |  | 3rd Party channel availability without having more than 3 HOP (source><DC><destination) |  |  | 97
MNO |  | All MNO Connectivity with Fiber Back Bone |  |  | 97
3 Datacenter Links |  | Lambda ring network connectivity for DC, NDC, DR |  |  | 99.9999
Lambda speed |  | PDC to NDC or FDC is 2ms< ¦ PDC & NDC to FDR 3ms<
Maintenance on DC |  | Manned maintenance |  |  | 99
Monitoring |  | Network monitoring services |  |  | 98
Goal |  | UFCL Service Uptime Assurance to 99.99% |  |  | 99.9999
Describe Project Risks, Constraints, and Assumptions
Risks |  | 1. Changes to Project Scope - Project needs to stay focused on root causes behind the source data and not expand the project into developing system requirements for problems with various applications. 2. Bad Data - The availability of cost data within the Project Management System may be so poor that even a basic level of performance cannot be established. 3. Implementation of Solutions - This project will most likely require changes in how Project Managers currently capture and process cost data. In some cases, Project Managers may resist and refuse to adopt these new procedures and recommendations. Thus, the problem with bad cost data will continue
Constraints |  | 1. Resources will be constrained to four full time FTE personnel + 1 System Administrator. The Agency does not have the budget to fund any additional resources for this project. 2. The project team will have direct access to Six Sigma Black Belts, but the project will be constrained by the fact that a Black Belt is not assigned full time to this project. 3. Programming support will be limited for the project and pulling extracts of data from source systems could be slow since a System Request must be submitted if canned extracts or queries are not available.
Assumptions |  | 1. The project is following a Six Sigma DMAIC approach. The agency has limited experience in doing projects according to this methodology. This project assumes that all stakeholders will understand and accept the six sigma related work products and deliverables. 2. This project has support from the CIO and the Director of the PMO. This project assumes that this sponsorship and support is sufficient to push successful implementation of solutions that result from this project.
Prepared by: |  | Shahab Al Yamin Chawdhury | Date: | 2021-08-20

## Migration-Checklist
Datacenter Migration Checklist
DFS SERVICES ¦ Datacenter Migration Tasks ¦ Movement from: Metronet DC
Document Code: IS/098 ¦ Prepared Date: 16th of September 2021 ¦ Next Review Date: Not required ¦ Confidentiality level: HBI
Move to
SL | Task | Task Description | Dependency | DC | NDC | DR | Remarks
1 | NDC Announcement | New NDC Confirmation Required |  |  | YES |  | 1. Consult DC developers for best DC establishment as Kaliakoir DC and a Lambda-Ring Network came alive on Oct-1st 2021, capable to provide a Lambda around 3 data centers, in 3 geographic locations with 2ms< transfer speed 2. DC & NDC Connection Required (Lambda) 3. BGP Announcement on 3 sites 4. IP Routes from 2 NTTN. 2ms< to DC & NDC with redundant Lambda. 3ms< ¦DC to DR and NDC to DR with redundant Lambda 5. 3rd Party Channel Routes (Confirm each routes to NDC) 6. MNO Routes (Confirm each routes to NDC) 7. BDIX Routes (Confirm each routes to NDC) 8. Massive Downtime Required for the last SwitchOver(12-15 days), or more HW needs to be populated in the NDC to ensure smoother transition 9. Movement time: 10 to 12 months, maybe longer 10. Manned NDC is required for at least 3Pax 11. New HW coming in 2021 will be housed in Metronet DC 12. New HW Requirements are lined up for FY22 will be housed in the newly selected PDC/SDC/FDR
|  | Internet for NDC |  |  | YES |  | Server & Application transfer & use (Current 60mbps-FD)
|  | To Transfer DC data to NDC (CCR) | DC with NDC | YES | YES |  | Gradually all servers will be connected to DC & NDC and will be moved to NDC
|  | Renounce NDC to PDC |  |  |  |  | NDC becomes PDC
2 | IP Announcement | BGP Announcement |  | YES | YES |  | First, BGP for NDC Needs to be configured, only then DC physical and/or virtual servers can be moved to NDC
|  | CloudFlare Route change to NDC | BGP Route | YES | YES |  | First, BGP for NDC Needs to be configured, only then DC can be moved to NDC
|  | BGP Route - Initiate | Purchase New IP for NDC | YES | YES |  | NDC Needs to be ready prior to move a datacenter
|  | All DC Hardware will be moved to the NDC |  |  |  |  | Prior to that the NDC needs to be equipped with Internet routes
|  | All Channel IP will be changed |  | YES | YES |  | Reconnection required for all 3rd party integrations
|  | Start adding new nodes in NDC |  | YES | YES |  | Kubernetes (MN, WN, DBN), CEPH (Clusters) etc. Afterwards, decommission the old nodes from old DC
3 | AppPlat Addition to NDC | Application Platform |  | YES | YES |  | New Kubernetes, CEPH Cluster needs to be developed first, when completed, afterwards DC nodes can be shut off, and move the Physical HW to NDC for immediate node addition
|  | CEPH Cluster Initiation | DC to NDC connectivity | YES | YES |  | Build new cluster in NDC, and gradually turn off the CEPH-DC nodes, move the HW to new PDC, reconnect and increase the CEPH nodes
|  | Git Connection to New DC | HQ to New DC | YES | YES |  | Reconfigure App Git Repo to connect to new DC
|  | App Monitors |  |  |  |  | Reconfigure and reconnect from NOC
4 | Hardware Movement | NDC Hardware establishment required |  | YES | YES |  | DC devices cannot be moved to NDC, if the DC HW is not ready. To move DC HW, a replica of DNC HW is required
|  | PaloAlto Firewall |  | YES | YES |  | Complete reconfiguration required
|  | Firewall - UTM |  | YES | YES |  | Complete reconfiguration required
|  | DELL Blade Servers |  | YES | YES |  | Complete reconfiguration required
|  | DELL Servers |  | YES | YES |  | Complete reconfiguration required
|  | Cisco Routers (VPN) |  | YES | YES |  | Complete reconfiguration required
|  | Cisco Switches |  | YES | YES |  | Complete reconfiguration required
|  | Cisco FI Switches |  | YES | YES |  | Complete reconfiguration required
|  | F5 Load Balancers |  | YES | YES |  | Complete reconfiguration required
|  | DELL SAN Storage with SAN Server |  | YES | YES |  | Complete reconfiguration required
|  | Monitoring Software (Various) |  | YES | YES |  | Complete reconfiguration required
|  | Mikrotik Routers (VPN) |  | YES | YES |  | Complete reconfiguration required
5 | Audit | [5 empty] | PCI-DSS Audit will be impacted as network design & different route changes
EY - Application Platform Audit will be impacted
VAPT on all new DC, NDC and DR

## Inventory-DC
DC Network Devices
SN | Device Type | Brand | Qty | Model | Serial / Part / Service Tag | Operating System | IP Address | Order Name | Purpose
1 | Switch | Cisco | 1 | C9200L-24T-4G-E | JAE24380W8T | Cisco IOS XE Software, Version 16.12.04 | 172.17.3.132 | WAN Switch
2 | Router | Cisco | 1 | ISR4461/K9 | FDO2435M0M2 | Cisco IOS XE Software, Version 17.03.02 | 172.17.3.134 | Core Router
3 | Router | Cisco | 1 | ISR4331-SEC/K9 | FDO2438M1NV | Cisco IOS XE Software, Version 16.12.03 | 172.17.3.136 | VPN Router
4 | Switch | Cisco | 1 | C9500-16X-E | FOC2435L564 | Cisco IOS XE Software, Version 16.12.04 | 172.17.3.137 | Core Switch
5 | Switch | Cisco | 1 | N9K-C93180YC-EX | FDO2437196H | NXOS: version 9.3(4) | 172.17.3.139 | Server Farm Switch
6 | Firewall | Paloalto | 1 | PA3220 | 016201025375 | PAN OS 9.1.5 | 172.17.3.144 | Firewall
7 | Load Balancer/WAF | F5 | 1 | F5-BIG-LTM-I2800 | f5-irdz-brkw | BIG-IP 15.1.2 Build 0.0.9 Final | 172.17.3.142 | Load Balancer
8 | Switch | Dell | 1 | Dell Networking N1500 | CN0G62KT282980850383A04 | 6.3.3.14 | 172.17.3.141 | Management Switch
9 | Switch | Cisco | 1 | C9200L-24T-4G-E | JAE24380VG4 | Cisco IOS XE Software, Version 16.12.04 | 172.17.3.133 | WAN Switch
10 | Router | Cisco | 1 | ISR4461/K9 | FD02438M1J1 | Cisco IOS XE Software, Version 17.03.02 | 172.17.3.135 | Core Router
11 | Switch | Cisco | 1 | C9500-16X-E | FOC2435L52U | Cisco IOS XE Software, Version 16.12.04 | 172.17.3.138 | Core Switch
12 | Switch | Cisco | 1 | N9K-C93180YC-EX | FDO2437196G | NXOS: version 9.3(4) | 172.17.3.140 | Server Farm Switch
13 | Firewall | Paloalto | 1 | PA3220 | 016201025421 | PAN OS 9.1.5 | 172.17.3.145 | Firewall
14 | Load Balancer/WAF | F5 | 1 | F5-BIG-LTM-I2800 | f5-eyae-maeo | BIG-IP 15.1.2 Build 0.0.9 Final | 172.17.3.143 | Load Balancer
15 | Switch (Fabric) | Dell | 1 | Dell EMC MX9116n | 34X5X63 | 10.5.0.7.745 | 172.17.3.19 | Fabric Switch
16 | Switch (Fabric) | Dell | 1 | Dell EMC MX9116n | 34X2X63 | 10.5.0.7.745 | 172.17.3.20 | Fabric Switch
17 | Switch (SAN) | Dell | 1 | CTX DS-6610B | BRCEZL1926R0CG | FOS version = v8.2.1c | 172.17.3.29 | SAN Switch
18 | Switch (SAN) | Dell | 1 | CTX DS-6610B | BRCEZL1926R0CV | FOS version = v8.2.1c | 172.17.3.30 | SAN Switch
19 | DC-MTK-RTR | Mikrotik | 1 | CCR1036-8G-2S+ | D83A0C58FFC8 |  | 172.17.3.147 | Remote Access VPN Router
DC Server
20 | Chassis | Dell | 1 | MX 7000 | 34X4X63 |  |  | Blade Chasis
21 | Blade Server | Dell | 1 | PE MX740C | 34Y1X63 | Windows Server 2019 DC Edition | 172.17.14.3 | Blade Srv 1 | Microsoft Solution, ERPs, DNS
22 | Blade Server | Dell | 1 | PE MX740C | 34X8X63 | Windows Server 2019 DC Edition | 172.17.14.4 | Blade Srv 2 | Microsoft Solution, ERPs, DNS
23 | Blade Server | Dell | 1 | PE MX740C | 34Y3X63 | RHEL 8.3 | 172.17.17.11 | Blade Srv 3 | Upay App Node
24 | Blade Server | Dell | 1 | PE MX740C | 34Y5X63 | RHEL 8.3 | 172.17.17.12 | Blade Srv 4 | Upay App Node
25 | Blade Server | Dell | 1 | PE MX740C | 34X6X63 | RHEL 8.3 | 172.17.17.13 | Blade Srv 5 | Upay App Node
26 | Blade Server | Dell | 1 | PE MX740C | 34X7X63 | RHEL 8.3 | 172.17.17.14 | Blade Srv 6 | Upay DB Node
27 | Blade Server | Dell | 1 | PE MX740C | 34Y2X63 | RHEL 8.3 | 172.17.17.15 | Blade Srv 7 | Upay DB Node
28 | Blade Server | Dell | 1 | PE MX740C | 34Y4X63 | RHEL 8.3 | 172.17.17.16 | Blade Srv 8 | Upay DB Node
29 | Rack Server | Dell | 1 | PE R640 | JTLTB33 | RHEL 8.3 | 172.17.16.17 | HSM-1 | Upay Master Node
30 | Rack Server | Dell | 1 | PE R640 | GTLTB33 | RHEL 8.3 | 172.17.16.18 | HSM-2 | Upay Master Node
31 | Rack Server | Dell | 1 | PE R640 | 1VLTB33 | RHEL 8.3 | 172.17.16.19 | HSM-3 | Upay Master Node
32 | Rack Server | Dell | 1 | PE R740XD | J66N053 | RHEL 8.3 | 172.17.10.10 | APP-Deploy-1 | Staging Server
33 | Rack Server | Dell | 1 | PE R740XD | J66P053 | Windows Server 2019 DC Edition | 172.17.14.6 | APP-Deploy-2 | Monitoring, Log
34 | Rack Server | Dell | 1 | PE R640 | 2VLTB33 | Windows Server 2019 DC Edition | 172.17.14.7 | Mgmt Server | Device Management
Storage & Backup
35 | IDPA | Dell | 1 | DP4400 | BBZN363 |  |  | Backup
36 | Storage | Dell | 1 | SC5020 | J5ZFX53 |  |  | Storage
37 | St0rage Enclosure | Dell | 1 | SC420 | J5ZDX53 |  |  | Starage Enclosure
Accessories
38 | KVM Switch | Dell | 1 | AV2216 | 0520358143 |  |  | KVM Switch
39 | KVM Monitor | Dell | 1 | KMMLED156 | 0580001006 |  |  | KVM Monitor
40 | PDU (24 Port) | APC | 4
41 | PDU (12 Port) | APC | 2
42 | Rack | APC | 2
43 | 10G DAC Cable | Cisco | 100 | SFP-H10GB-CU3M=
44 | SFP Module | Cisco | 8 | SFP-10G-SR=
45 | Copper Module | Cisco | 8 | GLC-TE=

## Inventory-DR
DC Network Devices
SN | Device Type | Brand | Qty | Model | Serial / Part / Service Tag | Operating System | IP Address | Order Name | Purpose
1 | Switch | Cisco | 1 | C9200L-24T-4G-E | JAE24330W61 | Cisco IOS XE Software, Version 16.12.04 | 172.18.3.132 | WAN Switch
2 | Switch | Cisco | 1 | C9200L-24T-4G-E | JAE24380W1U | Cisco IOS XE Software, Version 16.12.04 | 172.18.3.133 | WAN Switch
3 | Router | Cisco | 1 | ISR4461/K9 | FDO2438M1TW | Cisco IOS XE Software, Version 17.03.02 | 172.18.3.134 | Core Router
4 | Router | Cisco | 1 | ISR4331-SEC/K9 | FDO2438M1NY | Cisco IOS XE Software, Version 17.03.02 | 172.18.3.136 | VPN Router
5 | Switch | Cisco | 1 | C9500-16X-E | FOC2435L51D | Cisco IOS XE Software, Version 16.12.04 | 172.18.3.137 | Core Switch
6 | Switch | Cisco | 1 | N9K-C93180YC-EX | FDO2437196F | NXOS: version 9.3(4) | 172.18.3.139 | Server Farm Switch
7 | Firewall | Paloalto | 1 | PA3220 | 016201025419 | PAN OS 9.1.6 | 172.18.3.144 | Firewall
8 | Load Balancer/WAF | F5 | 1 | F5-BIG-LTM-I2800 | f5-syjz-zhix | BIG-IP 14.1.2.6 Build 0.0.2 Point Release 6 | 172.18.3.142 | Load Balancer
9 | Switch | Dell | 1 | Dell Networking N1500 | CN0G62KT282980850029A04 | 6.3.3.14 | 172.18.3.141 | Management Switch
10 | Switch (Fabric) | Dell | 1 | Dell EMC MX9116n | 35H9X63 | 10.5.0.7.745 | 172.18.3.19 | Fabric Switch
11 | Switch (Fabric) | Dell | 1 | Dell EMC MX9116n | 35K9X63 | 10.5.0.7.745 | 172.18.3.20 | Fabric Switch
12 | Switch (SAN) | Dell | 1 | CTX DS-6610B | BRCEZL1926R0D0 | FOS version = v8.2.1c | 172.18.3.29 | SAN Switch
13 | Switch (SAN) | Dell |  | CTX DS-6610B | BRCEZL1926R0CZ | FOS version = v8.2.1c | 172.18.3.30 | SAN Switch
DR Server
14 | Chasis | Dell | 1 | MX 7000 | 35L1X63 |  | 172.18.3.9 | Blade Chasis
15 | Blade Server | Dell | 1 | PE MX740C | 35J6X63 | RHEL 8.3 | 172.18.10.11 | Blade Srv 1 | Upay Master & App Node
16 | Blade Server | Dell | 1 | PE MX740C | 35J7X63 | RHEL 8.3 | 172.18.10.12 | Blade Srv 2 | Upay Master & App Node
17 | Blade Server | Dell | 1 | PE MX740C | 35J8X63 | RHEL 8.3 | 172.18.10.13 | Blade Srv 3 | Upay Master & App Node
18 | Blade Server | Dell | 1 | PE MX740C | 35J9X63 | RHEL 8.3 | 172.18.10.14 | Blade Srv 4 | Upay DB Node
19 | Blade Server | Dell | 1 | PE MX740C | 35K3X63 | RHEL 8.3 | 172.18.10.15 | Blade Srv 5 | Upay DB Node
20 | Blade Server | Dell | 1 | PE MX740C | 35K5X63 | RHEL 8.3 | 172.18.10.16 | Blade Srv 6 | Upay DB Node
21 | Rack Server | Dell | 1 | PE R640 | HTLTB33 | Windows Server 2019 DC Edition | 172.18.14.7 | Management Server | Device Management
Storage & Backup
22 | IDPA | Dell | 1 | DP4400 | CBZN363 |  | 172.18.3.27 | Backup |  | keep the mgmt IP in the cell during on IDPA it will be assigned.
23 | Storage | Dell | 1 | SC5020 | J62CX53 | version 7.4.10.27 | 172.18.3.5 | Storage
24 | Storage | Dell | 1 | SC420 | J61WG53 |  |  | Storage Enclosure
Accessories
25 | KVM Switch | Dell | 1 | AV2216 | 0520358171 |  | 172.18.3.45
26 | KVM Monitor | Dell | 1 | KMMLED156 | 0580001005
27 | PDU (24 Port) | APC | 4
28 | RACK | APC | 2
29 | 10G DAC Cable | Cisco | 20 | SFP-H10GB-CU3M=
30 | SFP Module | Cisco | 4 | SFP-10G-SR=
31 | Copper Module | Cisco | 4 | GLC-TE=