## Phase-I
Services | Sub Category | Core Product/Service | Scource | Client | Requirements | Delivery | Responsible Person | Implementation | Required Resources | Progress | Designation | Start Time | End Time
Network Environment Deployment | Resource Management | Intranet Access | In-House | UCBL | DELL R740XD2 | Development Services | Shahab | Redmine | Administrator | 0
[7 empty] | Shahab | CloudFlare | Administrator | 0
[7 empty] | Shahab | Development Environment | Administrator | 0
[7 empty] | Shahab | Staging Environment | Administrator | 0
[7 empty] | Shahab | Production Environment | Administrator | 0
[7 empty] | Shahab | Deploy all Relevant VM's | Administrator | 0
[6 empty] | Network Services | Shahab | Establish Internet & Intranet | Administrator | 0
[7 empty] | Shahab | Domain authority transfer | Administrator | 0
[7 empty] | Shahab | Deploy WiFi AP's | Administrator | 0
[7 empty] | Shahab | Migrate all Certificate Credentials | Administrator | 0
[7 empty] | Shahab | Migrate All VPN Credentials | Administrator | 0
[7 empty] | Shahab | Sanitize | Administrator | 0
[6 empty] | Access Controls | Shahab | Deploy Domain Controller | Administrator | 0
[7 empty] | Shahab | Enroll All PC's | Administrator | 0
[7 empty] | Shahab | Deploy SCEP | Administrator | 0
[7 empty] | Shahab | Deploy Physical Access Controls | Administrator | 0
[7 empty] | Shahab | Enroll All Cards | Administrator | 0
[7 empty] | Shahab | Test: Failover & Failback | Administrator | 0
[6 empty] | Security Controls | Shahab | Development Security | Administrator | 0
[7 empty] | Shahab | Network Security | Administrator | 0
[7 empty] | Shahab | PC Security | Administrator | 0
[7 empty] | Shahab |  | Administrator | 0
[6 empty] | SCCM & SCEP | Shahab | Deploy SCCM for Inventory Recall | Administrator | 0
[7 empty] | Shahab | Deploy Distribution Point | Administrator | 0
[7 empty] | Shahab |  | Administrator | 0
[7 empty] | Shahab |  | Administrator | 0
|  | Storage | In-House | UCBL | DELL R740XD2 | Storage Deployment | Shahab | Replica Deployment | Administrator | 0
[7 empty] | Shahab | VM Cluster Services | Administrator
[7 empty] | Shahab | Certificate Import | Administrator
[7 empty] | Shahab | Develop the site | Administrator | 0
[7 empty] | Shahab | Test the site | Administrator | 0
[7 empty] | Shahab | LACP Link Aggregation | Administrator | 0
[7 empty] | Shahab |  | Administrator | 0
[7 empty] | Shahab |  | Administrator | 0
|  | Back-office | In-House | UCBL | DELL R740XD2 | Failover/Failback | Shahab | Application Cluster Deployment | Administrator | 0
[7 empty] | Shahab | VM Replica Pool Deployment | Administrator | 0
[7 empty] | Shahab | Failover/Failback Deployment | Administrator | 0
[7 empty] | Shahab | Test Failover/Failback | Administrator | 0
[7 empty] | Shahab |  | Administrator | 0
[7 empty] | Shahab |  | Administrator | 0
[7 empty] | Shahab |  | Administrator | 40

## 3Yrs RoadMap
Services | Sub Category | Core Product/Service | Scource | Client | Requirements | Delivery | Responsible Person | Implementation | Required Resources | Progress | Designation | Start Time | End Time
Active Directory Implementation | Resource Management | Internet Access | In-House | UCBL |  | Active Directory Deployment | Shahab | Domain Name registration Information collected | Administrator | 100
[7 empty] | Shahab | Improvements & stabilize | Administrator | 100
[7 empty] | Shahab | Domain parking | Administrator | 100
[7 empty] | Shahab | Test the site Properties | Administrator | 100
[7 empty] | Shahab | Test the site | Administrator | 100
[7 empty] | Shahab | Upload Content Off-Portal | Administrator | 100
[5 empty] | DELL R740XD2 | Client Enrollment | Shahab | Client Join | Administrator | 100
[7 empty] | Shahab | Domain authority transfer | Administrator | 100
[5 empty] | Win2k19 DAT |  | Shahab | Existing domain to park | Administrator | 100
[7 empty] | Shahab | DNS Stabilization | Administrator | 100
[7 empty] | Shahab | Test the site | Administrator | 100
[7 empty] | Shahab | Upload Content at the site | Administrator | 100
[7 empty] | Shahab | Laptop Rapid Deployment | Administrator | 100
[6 empty] | ADC Deployment | Shahab | Deploy Additional Domain Controller | Administrator | 100
[7 empty] | Shahab | Develop the site | Administrator | 100
[7 empty] | Shahab | Test the site | Administrator | 100
[7 empty] | Shahab | Register the domain | Administrator | 100
[7 empty] | Shahab | Upload the site | Administrator | 100
[7 empty] | Shahab | Test Failover & Failback | Administrator | 100
[6 empty] | Certificate Services | Shahab | Enroll for DirectAccess | Administrator | 0
[6 empty] | DirectAccess | Shahab | Connectivity Test | Administrator | 0
[7 empty] | Shahab | UC Certificate Enrollment | Administrator | 0
[7 empty] | Shahab | Enroll Storage with AD | Administrator | 100
[6 empty] | SCCM & SCEP | Shahab | Deploy SCCM for Inventory Recall | Administrator | 100
[6 empty] | Deployment | Shahab | Primary Site Deployment | Administrator | 100
[7 empty] | Shahab | Test the site | Administrator | 100
[7 empty] | Shahab | Deploy Monitoring Server | Administrator | 100
[7 empty] | Shahab | Deploy SQL Datawarehouse | Administrator | 100
[7 empty] | Shahab | Upstream/Downstream Collection | Administrator | 50
[6 empty] | IT-CMF, ISO-27001 Framework, Cyber Security Framework, TOGAF | Shahab | Deploy IT-CMF | Administrator | 0
[7 empty] | Shahab | Deploy 20000 ITSM Framework | Administrator | 0
[7 empty] | Shahab | Deploy CI-SECURITY Framework | Administrator | 0
[7 empty] | Shahab | Deploy TOGAF Enterprise Architecture Framework | Administrator | 0
[7 empty] | Shahab | Alinean IO Analysis | Administrator | 100
[7 empty] | Shahab | Cloud Security Readiness Tool | Administrator | 100
[7 empty] | Shahab | IT Deployment Framework | Administrator | 100
[7 empty] | Shahab | Deploy 27001 IS Mandatory Framework | Administrator | 0
|  | E-Mail Hosting | In-House | UCBL | DELL R740XD |  | Shahab | Replica Deployment | Administrator | 100
[7 empty] | Shahab | Stabilize Connectivity | Administrator | 50
[5 empty] | Win2k12R2 DAT |  | Shahab | Certificate Import | Administrator | 0
[7 empty] | Shahab | Develop the site | Administrator | 100
[5 empty] | SCCM2012R2 DAT |  | Shahab | Test the site | Administrator | 100
[7 empty] | Shahab | Deploy Asset Management | Administrator | 100
[7 empty] | Shahab | Deploy Security Information and Event Mgmt (SIEM) | Administrator | 0
[7 empty] | Shahab | Approve Policies | Administrator | 0
|  | Software Integration | In-House | UCBL | MIS, Quickbook, MQ, HR | AD Integration Test Completed, Ready to Integrate | Shahab | Host forwarding to Port 80 | Administrator | 100
[7 empty] | Shahab | Initiate NAP | Administrator | 0
[7 empty] | Shahab | Register for administrataion of domains and park all domains | Administrator | 100
[7 empty] | Shahab | Design for AD Failover/Failback | Administrator | 0
[7 empty] | Shahab | Arrange for disaster recovery options | Administrator | 0
[7 empty] | Shahab | Integrate to AD (Tested) | Administrator | 0
[7 empty] | Shahab | Deploy Disk Encryption |  | 0
[7 empty] | Shahab | Approve Enterprise Design |  | 0
[7 empty] | Shahab | Initiate SCDPM |  | 0
[7 empty] | Shahab | Initiate FIREWALL | Administrator | 0
Enterprise Mail Server
SharePoint Integration
Enterprise Portal Services
CorpNet
SQL Integration
Exchange Integration
SCSM
Unified Communication Server (Lync)
SQL Integration
SharePoint Integration
Exchange Integration
Enterprise Content Management