## Top line update
UCB DFS Project
Project Lead : Sydul H Khandaker
2020-06-01
[6 empty] | Month | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
[6 empty] | WK | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
| Key critical milestone for soft-launch | % | status | c/day | start | end
| Subsidiary company formation & BB approval | 70 | Company Formation done, BB Approval awaiting | 70 | 2020-06-01 | 2020-08-10 | [30 empty] | Company Secretary
| Business strategy & plan sign-off | 90 | Draft Strategy prepared, Board approval awaiting | 56 | 2020-06-15 | 2020-08-10 | [30 empty] | Chief Strategy Officer
| Business process define & sign-off | 50 | 80% Process Prepared, Approval awaiting | 40 | 2020-07-01 | 2020-08-10 | [30 empty] | Project Team
| Critical resource onboarding | 80 | Currently sales force onboarding(TM level) - WIP | 61 | 2020-06-07 | 2020-08-07 | [30 empty] | Head of HR
| Existing resource reallocation (ucash,upay employee) | 100 | Complete till soft-launch | 40 | 2020-07-01 | 2020-08-10 | [30 empty] | Head of HR
| Budget approval (Soft launch) | 0 | Done | 45 | 2020-07-01 | 2020-08-15 | [30 empty] | Poject Director
| Key Service & Hardware Procurement & WH buildup | 0 | Core HW Order placed | 76 | 2020-07-01 | 2020-09-15 | [30 empty] | Head of SCM
Tcech | DFS core platform readiness | 31 | Database clustering- Done, High level design, Kubernetes Node, Service design/micro service design complete, Middleware service (Core Component) - WIP | 62 | 2020-07-15 | 2020-09-15 | [30 empty] | Head of IT projects
| Ucash, Upay data sanitization & migration to new platform | 2 | Raw data received, mapping WIP | 92 | 2020-07-15 | 2020-10-15 | [30 empty] | Head of IT projects
| Apps development(Customer, Agent, DSO, Merchant) | 10 | DSO,Dist apps readiness 37% | 47 | 2020-08-15 | 2020-10-01 | [30 empty] | Head of IT projects
| Core hardware purchase & NOC commissioning | 0 | Waiting for hardware | 31 | 2020-08-15 | 2020-09-15 | [30 empty] | Head of IT projects
| Integration (MNO, NID Server, UCB-CBS & CMS, Payments gateway | 34 | 10 API received as of now, will be integrated once API gateway is ready | 70 | 2020-08-01 | 2020-10-10 | [30 empty] | Head of IT projects
| ERP and HRM solution readiness | 0 | Not Started yet | 61 | 2020-08-10 | 2020-10-10 | [30 empty] | Head of IT projects
| Sales force tracking software | 0 | Not Started yet | 56 | 2020-08-15 | 2020-10-10 | [30 empty] | Head of IT projects
| Basic reporting module readiness | 0 | Not Started yet | 31 | 2020-08-15 | 2020-09-15 | [30 empty] | Head of IT projects
| Channel commission structure finalization | 50 | Team working WIP, Will share this week | 45 | 2020-08-01 | 2020-09-15 | [30 empty] | Head of distribution sales
| Onboarding of distributor, Agent Merchant, B2B, G2B | 0 | Onbaording speech -draft ready, dependancy on strategy & finance | 55 | 2020-08-21 | 2020-10-15 | [30 empty] | Head of distribution sales
| Activate B2B/B2G team | 0 | Not started yet | 51 | 2020-08-10 | 2020-09-30 | [30 empty] | Head of B2B Sales
| Merchant acquisition kick off | 20 | Started, Team weekly share update-WIP | 46 | 2020-08-15 | 2020-09-30 | [30 empty] | Head of Merchant Acquistion
| Product & pricing finalization | 0 | Team working, Will share this week with PD | 51 | 2020-08-10 | 2020-09-30 | [30 empty] | Chief Strategy Officer
| Review, renewal, discontinuation of existing & new contract | 10 | Launch critical 40 agreements : 10 API received, EC server pending, Porichoy -WIP, | 127 | 2020-06-10 | 2020-10-15 | [30 empty] | Chief Strategy Officer
| All MNO (USSD & Top up) agreement renewal | 40 | BL initiated, Robi & GP negotiation WIP, Teletalk will delay. | 62 | 2020-07-15 | 2020-09-15 | [30 empty] | Chief Strategy Officer
| Major govt. utility agreements | 0 | Not Started yet | 61 | 2020-08-15 | 2020-10-15 | [30 empty] | Head of Govt. Sales
| Add money agreement with 15 banks |  | WIP, 12 Banks communicated till last week | 123 | 2020-07-15 | 2020-11-15 | [30 empty] | Head of Bank & FI partnership
| Bank agreement for lifting & refund |  | 5 Bank communication initiated, Rest WIP | 46 | 2020-08-15 | 2020-09-30 | [30 empty] | Chief Finance Officer
| New Brand name, Logo finalization & registration |  | Brand name fixed, Logo finalized pending | 77 | 2020-07-15 | 2020-09-30 | [30 empty] | Head of Market Development & Ops
| Creative agency onboarding |  | RFQ floating in magt decision pending | 37 | 2020-08-15 | 2020-09-21 | [30 empty] | Head of Market Development & Ops
| Digital agency onboarding |  | RFQ floating in magt decision pending | 37 | 2020-08-15 | 2020-09-21 | [30 empty] | Head of Market Development & Ops
| Website Development |  | RFQ floating in magt decision pending | 60 | 2020-08-01 | 2020-09-30 | [30 empty] | Head of Market Development & Ops
| PoSM design for agents & merchants |  | Logo dependancy, Sales requirement shared with Brand & SCM | 45 | 2020-08-01 | 2020-09-15 | [30 empty] | Head of Market Development & Ops
| PoSM vendor selection & printing |  | POSM detail speciafication is WIP at Sales opps team | 51 | 2020-08-10 | 2020-09-30 | [30 empty] | Head of Market Development & Ops
| Call Center readiness & Go Live |  | Proposal received from vendor, Technical evalution WIP | 73 | 2020-07-20 | 2020-10-01 | [30 empty] | Head of Market Development & Ops
| Existing customer data validation thru KYC management vendor |  | Not Started yet | 75 | 2020-08-01 | 2020-10-15 | [30 empty] | Head of Market Development & Ops
| Existing Upay & Ucash customer communication |  | Darft Ready, will close next week | 75 | 2020-08-01 | 2020-10-15 | [30 empty] | Head of Market Development & Ops
| Readiness of compliance, fraud reporting and awareness |  |  | 71 | 2020-08-20 | 2020-10-30 | [30 empty] | Head of Corporate & Regulatory Aff.
| Initiate PR & external communication |  | Plan innitiated, will share next wk. | 47 | 2020-08-15 | 2020-10-01 | [30 empty] | Head of Market Development & Ops
| Launch check list ready |  |  | 10 | 2020-09-15 | 2020-09-25 | [30 empty] | Project Manager
| Soft Launch –Go Live |  |  |  | to be disclosed | [31 empty] | PD

## Work Breakdown Structure (WBS)
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | UCB DFS Project | [6 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | Project Lead : Sydul H Khandaker | [6 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. |  |  | Project Start Date: |  | 2020-06-01
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. |  |  | Scrolling Increment: |  | 60 |  |  | July | [6 empty] | August | [27 empty] | September
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | Project Manager : Mamun Ferdoushi | time axis 2020-07-31 to 2020-09-24
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart. | NB : Press 1 or 2 to expand or collaps the data from the left corner
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Category | Assigned To | Progress | Start | No. Days | Column1 | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Subsidiary Company Formation | On Track | Project Director | 85% | 2020-06-01 | 70
| Board resolution for DFS subsidiary formation under PSO/PSP license | Milestone |  | 100% | 2020-03-12 | 20
| Bangladesh Bank approval along with PSO/ PSP license | High Risk |  | 0% | 2020-06-01 | 20
| MoA & AoA draft |  |  | 100% | 2020-03-12 | 20
| MoA & AoA finalization |  |  | 100% | 2020-03-12 | 20
| Registration of subsidiary under RJSC |  |  | 100% | 2020-03-12 | 20
| Trade license from Dhaka North City Corporation |  |  | 100% | 2020-06-01 | 30
| VAT Registration |  |  | 100% | 2020-06-01 | 30
| eTIN/ BIN Registration |  |  | 100% | 2020-06-01 | 30
| Deposit Paid up capital |  |  | 100% | 2020-03-12 | 20
| Organogram approval by board/ management |  |  | 100% | 2020-03-12 | 20
| Creating Company Bank Account |  |  | 100% | 2020-03-12 | 20
| On boarding of tier-1/ HoD level |  |  | 90% | 2020-06-01 | 45
| Legal vetting of business scope |  |  | 0% | 2020-04-01 | 30
| Business Plan & Strategy Development | On Track | Ziaur Rahman | 80% | 2020-06-15 | 56
| Phase wise product priority setting submission |  |  | 100% | 2020-06-16 | 15
| Phase wise product priority setting approval |  |  | 100% | 2020-06-22 | 7
| Strategy workshop for business plan |  |  | 100% | 2020-06-20 | 7
| Respective function to submit their plan |  |  | 70% | 2020-06-23 | 2
| Final Business plan & Strategy submission to the Project Director |  |  | 0% | 2020-07-30 | 6
| Final Business plan & Strategy submission to the board |  |  | 0% | 2020-08-07 | 15
| Business plan (along with top line strategy) approval by the board |  |  | 0% | 2020-08-25 | 7
| Business Process readiness & sign-off | On Track | PM |  | 2020-07-05 | 60
| 1.SCM Process |  | Akram | 100% | 2020-07-05 | 10
| 2. Distributor on boarding process |  | Nasir | 100% | 2020-07-05 | 15
| 3.Agent on boarding process |  | Nasir | 100% | 2020-07-05 | 35
| 4. Merchant onboarding process |  | Rezwanul | 100% | 2020-07-05 | 60
| 5.Customer acquisition/registration process |  | Nasir |  | 2020-07-05 | 24
| 6.Customer Bulk registration process |  | Nazim | 100% | 2020-07-05 | 15
| 7. AML CFT process (Anti-Money Laundering & Countering the Financing of Terrorism Process) |  | to be |  | 2020-07-05 | 24
| 8.Lifting & refund process |  | Nasir |  | 2020-07-05 | 15
| 9. Commission disbursement process |  | Nasir |  | 2020-07-05 | 15
| 10. Customer complain handling process |  | Jesan |  | 2020-07-05 | 18
| 11. Complain (fraud/ LEA related) handling process |  | Mahbubur |  | 2020-07-05 | 24
| 12. HR Process |  |  |  | 2020-07-05 | 24
| 13. FDoA (Financial Delegation of Authority) |  | Siddiquee |  | 2020-07-05 | 24
| Critical Resource onboarding & HR Mgt | On Track | Ahmed Pasha | 80% | 2020-06-01 | 100
| Develop recruitment and employee on boarding process |  |  | 100% | 2020-06-10 | 15
| Organogram approval by board/ management |  |  | 100% | 2020-07-01 | 21
| Recruitment requisition preparation and mgt. approval |  |  | 100% | 2020-07-09 | 7
| Headcount and budget forecast sharing with management |  |  | 100% | 2020-07-12 | 7
| Draft HR Policy & Guidelines (manual) submission |  |  | 0% | 2020-07-21 | 45
| Defining all job role |  |  | 0% | 2020-07-15 | 60
| KPI Define & approval from the management |  |  | 0% | 2020-07-15 | 60
| Recruitment interview & selection for tier-1, 2,3 |  |  | 90% | 2020-07-01 | 60
| Laptop/desktop /others requisition to IT |  |  | 90% | 2020-07-01 | 60
| On boarding of tier-1, 2, 3 |  |  | 80% | 2020-07-01 | 75
| Existing resource reallocation | On Track |  | 100% | 2020-07-01 | 40
| Budget approval (Soft launch) | On Track |  | 100% | 2020-07-01 | 30
Technology
| Technology : Technology Architecture Planning & Deployment | On Track | Tech Head | 30% | 2020-07-10 | 21
| Technology planning & system |  | Shahab | 100% | 2020-04-10 | 7
| Tech system detail plan and budget submission |  | Shahab | 100% | 2020-04-10 | 5
| Tech system detail plan and budget approval | On Track | Project Director |  | 2020-07-15 | 5
| Aggregator integration_ITCL |  | BackEnd |  | 2020-09-15 | 5
| Bank API Integration |  | BackEnd |  | 2020-10-15 | 5
| Payment Gateway API Integration |  | BackEnd |  | 2020-10-15
| e-Commerce Platform API Integration |  | BackEnd |  | 2020-10-15
| International Remittance Services API Integration |  | BackEnd |  | 2020-10-15
| Bill Payment Merchant API Integrations |  | BackEnd |  | 2020-10-15
| Value Added Service Merchant API Integration |  | BackEnd |  | 2020-10-15
| Integration with Google mapping |  | BackEnd |  | 2020-10-15
| Integration with NPSB for other banks fund transfer (Add money) |  | Arch |  | 2020-10-15
| Recruitment requisition to HR |  | Tech Head |  | 2020-04-10
| Recruitment interview for tier-3 |  | Tech Head |  | 2020-06-01
| Final selection and appointment letter issue of tier-3 |  | Tech Head |  | 2020-06-01
| On boarding of tier-3 |  | Tech Head |  | 2020-07-01
| Recruitment interview for tier-2 |  | Tech Head | 80% | 2020-06-01
| Final selection and appointment of tier-2 |  | Tech Head |  | 2020-06-01
| On boarding of tier-2 |  | Tech Head |  | 2020-07-01
| Recruitment interview for tier-1 |  | Tech Head | 50% | 2020-08-01
| Final selection and appointment of tier-1 |  | Tech Head |  | 2020-08-16
| On boarding of tier-1 |  | Tech Head |  | 2020-10-01
| Team KPI submission |  | Tech Head |  | 2020-08-01
| Team KPI management approval |  | PD |  | 2020-09-01
| DFS Platform Development | On Track | Tech Head |  | 2020-07-12 | 110
| DFS platform requirment compilation - SRS Pending |  | Business |  | 2020-07-15 | 20
| Functional Business requirement collection from relevant stakeholders |  | Business
| Functional Business requirement draft submission |  | Business
| Functional Business requirement signoff |  | Project director
| Prepare SRS (Software requirement Specification) |  | Manik/Business Team
| SRS signoff |  | Project Director
| Detail project roadmap submission |  | Shahab | 100%
| Hardware & associated 5 yrs infra installation |  | Shahab | 100%
| DR site & Replica installation plan |  | Shahab | 100%
| MNO connectivity establishment |  | Nazim
| 3rd party integration |  | BackEnd
| UCASH Existing DB data migration |  | BackEnd
| UCASH USSD Module Integration/Migration |  | BackEnd
| UPAY Existing DB data migration |  | BackEnd
| Phase-1 deployment activity finish |  | BackEnd
| Phase-1 UAT |  | BackEnd
| Phase-1Testing& Bug fixing |  | BackEnd
| Platform handover to DFS team |  | BackEnd
| Platform live with phase-1 requirment |  | BackEnd
App Development
| Application Platform Architecture Design Plan | On Track | Shahab |  | 2020-07-15 | 78
(1) Customer App Workshop
Customer app requirement compilation
Customer app requirement finalization (functional & UI UX) & Signoff
Customer app development RFQ float with the vendors
Customer app, Vendor proposal submission
Technical evaluation of vendors and short listing
Commercial negotiation with vendor
Customer app vendor management approval
Customer app vendor PO issue
Customer app development kick off
Customer app UI/UX development and management review
Customer app final UI/UX development and management approval
Customer app Beta release
Customer app UAT
Customer app bug fixing
App Terms & Conditions development
App Terms & Conditions legal vetting
Customer app final release in app store (Android version)
Customer app final release in app store (iOS version)
Agent app Project team formation & Charter signoff
Agent app requirement compilation
Agent app requirement finalization (functional & UI UX) & Signoff
(2) Agent app development RFQ float with the vendors
Agent app, Vendor proposal submission
Technical evaluation of vendors and short listing
Commercial negotiation with vendor
Agent app vendor management approval
Agent app vendor PO issue
Agent app development kick off
Agent app UI/UX development and management review
Agent app final UI/UX development and management approval
Agent app bug fixing
Agent app Beta release
Agent app UAT
Agent app final release in app store (Android version)
DSO app project team formation and project charter signoff
(3) DSO App Requirement Compilation
DSO app requirement finalization (functional SRS & UI/UX) & Signoff
Distribution management system (DMS) development
Distribution management system (DMS) live
DSO app development RFQ float with the vendors
DSO app, Vendor proposal submission
Technical evaluation of vendors and short listing
Commercial negotiation with vendor
DSO app vendor management approval
DSO app vendor PO issue
DSO app SRS UI/UX development and management review
DSO app SRS final UI/UX development and management approval
DSO app development kick off
DSO app bug fixing
DSO app Beta release
DSO app UAT
DSO app final release in app store (Android version)
(4) Merchant app requirement compilation
Merchant app requirement finalization (functional SRS & UI/UX) & Signoff
Merchant app development RFQ float with the vendors
Merchant app, Vendor proposal submission
Technical evaluation of vendors and short listing
Commercial negotiation with vendor
Merchant app vendor management approval
Merchant app vendor PO issue
Merchant app SRS UI/UX development and management review
Merchant app SRS final UI/UX development and management approval
Merchant app development kick off
Merchant app bug fixing
Merchant app Beta release
Merchant app UAT
| Merchant app final release in app store (Android version) |  |  |  | 2020-10-01
To be add more milestone
| Key Service & Hardware Procurement & WH buildup (SCM) | On Track | Akram |  | 2020-06-01 | 120
| Procurement | On Track |  | 71% | 2020-06-10 | 90
| Procurement Process Development and submission |  |  | 100% | 2020-06-10 | 15
| Procurement Policy Development and submission |  |  | 100% | 2020-06-20 | 10
| Procurement policy & process management approval |  |  | 50% | 2020-06-20 | 10
| Team role definition and job profile |  |  | 100% | 2020-06-20 | 10
| On boarding of Procurement team |  |  | 60% | 2020-07-20 | 30
| Prepare & get approved BoQ for Tech Hardware purchase |  |  | 100% | 2020-06-01 | 60
| Purchase Tech Hardware for launch critical |  |  | 80% | 2020-06-01 | 90
| Prepare list of service/Product to prucure by discussing stakeholders |  |  | 0% | 2020-08-01 | 10
| Purchase launch critical Product & service |  |  | 50% | 2020-09-01 | 30
| Logistics & Warehousing | On Track | Akram |  | 2020-07-01 | 90
| Warehouse location sourcing |  |  | 100% | 2020-06-10 | 15
| Warehouse location management approval |  |  | 100% | 2020-06-20 | 10
| Transport/ courier service sourcing |  |  | 0% | 2020-06-20 | 10
| Transport/ courier service vendor management approval |  |  | 0% | 2020-06-20 | 10
| Logistics/warehouse management SOP submission |  |  | 100% | 2020-06-20 | 10
| Logistics/warehouse management SOP sign off |  |  | 0% | 2020-06-20 | 10
| Team role definition and job profile |  |  | 100% | 2020-08-16 | 15
| Recruitment requisition to HR |  |  | 100% | 2020-08-16 | 15
| On boarding of warehouse employee |  |  | 0% | 2020-08-16 | 15
| Warehouse policy & process prepardness & mgt approval |  |  | 100% | 2020-08-16 | 15
| Channel commission structure finalization | On Track | Biplab Banerjee |  | 2020-08-01 | 30
| Channel commission structure Prepare & approved |  |  | 80% | 2020-08-01 | 30
| Business Operation ( onboarding of distributor, agent, retailer) | On Track | Biplab Banerjee | 21.11% | 2020-06-01 | 120
| Sales_distribution (Channel readiness) |  |  |  |  | 0
| Channel strategy and roll out roadmap development |  |  | 100% | 2020-06-10 | 28
| Acquisition strategy development and submission |  |  | 100% | 2020-06-15 | 9
| Transaction & Cash management strategy development and submission |  |  | 20% | 2020-06-20 | 10
| Strategy review by management and approval |  |  | 50% | 2020-06-25 | 10
| Team structure finalization |  |  | 100% | 2020-06-15 | 5
| Team role definition and job profile |  |  | 100% | 2020-06-15 | 10
| Recruitment requisition to HR |  |  | 100% | 2020-06-25 | 5
| Recruitment interview done |  |  | 70% | 2020-06-15 | 22
| Final selection and appointment of tier 1 |  |  | 100% | 2020-07-20 | 30
| Distributor appointment criteria & process submission |  |  | 100% | 2020-06-15 | 9
| Distributor appointment process management approval |  |  | 0% | 2020-06-24 | 10
| Retailier appointment criteria & process submission |  |  | 100% | 2020-06-15 | 9
| Retailier appointment process management approval |  |  |  | 2020-06-24 | 10
| Geographic demarkation preparation with mapping (Region/ Area/Territory) |  |  | 100% | 2020-07-03 | 7
| Screening & review of existing channel partners |  |  | 0% | 2020-07-15 | 20
| Territory wise potential distributors document collection |  |  | 10% | 2020-08-01 | 90
| Channel partner/ distributor screening |  |  |  | 2020-08-07 | 90
| Channel partner/ distributor short-listing |  |  |  | 2020-08-15 | 90
| Channel partner/ distributor appointment finish |  |  |  | 2020-11-15 | 1
| Distributor Field force on boarding |  |  |  | 2020-10-01 | 120
| Team KPI submission |  |  |  | 2020-07-20 | 7
| Team KPI management approval |  |  |  | 2020-07-25 | 5
| Sales Operation | On Track | Biplab Banerjee |  | 2020-04-10 | 129
| Distribution agreement draft preparation |  | Nasir | 100% | 2020-07-20 | 10
| Distribution agreement draft vetting |  | Nasir | 0% | 2020-07-26 | 5
| Distribution agreement draft_managment approval |  | Project Director | 0% | 2020-08-01 | 4
| All documents of distributor archieved |  | Nasir |  | 2020-08-01 | 90
| Entry of distributor data in the system |  | Nasir |  | 2020-08-15 | 60
| Distributors live in the system |  | Nasir |  | 2020-10-01 | 20
| Distributor's Bank A/C opening activity |  | Nasir |  | 2020-09-15 | 20
| Distributor's Banking information integration with company |  | Nasir |  | 2020-09-15 | 25
| Distribution SOP submission |  | Nasir |  | 2020-07-20 | 30
| Distribution SOP management approval |  | Project Director |  | 2020-08-20 | 5
| Cash management process management approval |  | Nasir | 90% | 2020-07-25 | 5
| Portal uses guideline (user manual) & arrange a training |  | Nasir |  | 2020-10-01 | 15
| Portal user access creation for distributors |  | Nasir |  | 2020-10-07 | 20
| Portal uses guideline (user manual) & arrange a training |  | Akram |  | 2020-07-15 | 16
| Field force monitoring app training |  | Nasir |  | 2020-08-14 | 17
| Field force monitoring app rollout |  | Nasir |  | 2020-09-15 | 15
| Develop forecast for KYC requirement |  | Nasir |  | 2020-09-15 | 15
| Channel Development & Commissioning | On Track | Head of Sales | 0% | 2020-08-07 | 97 | 97
| Alternate channel strategy & plan submission |  | Head of Sales |  | 2020-08-07 | 7 | 7
| Alternate channel strategy & plan approval |  | Head of Sales |  | 2020-08-10 | 3 | 3
| Start sourcing for International Remittance partners |  | Head of Sales |  | 2020-08-07 | 7 | 7
| Agreement signing International Remittance partners |  | Head of Sales |  | 2020-04-10 | 15 | 15
| Payment & Merchant | On Track | Nurul H Manik | 40% | 2020-05-05 | 130
Merchant Ecosystem development
| Payment and merchant strategy and plan submission |  |  | 50% | 2020-06-05
| Payment and merchant strategy and plan management approval |  |  |  | 2020-06-20 | 14
| Merchant acquisition and closure process submission |  |  | 50% | 2020-05-05 | 50
| Merchant acquisition and closure process signoff |  |  | 30% | 2020-06-16 | 30
| Team role definition and job profile |  |  |  | 2020-07-01 | 14
| On boarding of Merchant tier 1, 2, 3 |  |  |  | 2020-09-01 | 29
| Team KPI submission |  |  |  | 2020-08-07 | 7
| Team KPI management approval |  |  |  | 2020-08-16 | 15
| Merchant KYC field finalization (Standard, e-KYC other) |  |  |  | 2020-07-01 | 14
| Merchant KYC design draft |  |  |  | 2020-07-15 | 16
| Merchant KYC legal vetting |  |  |  | 2020-07-31 | 7
| Merchant KYC design finalization/ management apporval |  |  |  | 2020-08-07 | 7
| Merchant operation manual (for all merchant segments) draft submission |  |  |  | 2020-06-30 | 82
| Merchant operation manual management review & sign off |  |  |  | 2020-08-01 | 13
| Merchant branding/merchandizing plan submission |  |  |  | 2020-08-14 | 17
| Merchant branding/merchandizing plan approval |  |  |  | 2020-09-01 | 14
| Merchant communication/ campaign plan for awareness |  |  |  | 2020-08-01 | 13
| Enterprise Sales Channel ( B2B, G2B) | On Track | Zahid |  | 2020-07-01 | 60
| Enterprise business strategy & roadmap development (Corporate,SME, Govt.) |  |  |  | 2020-07-01 | 15
| Enterprise business strategy & roadmap management review and approval |  |  |  | 2020-07-16 | 7
| Team structure finalization |  |  |  | 2020-07-01 | 15
| Team role definition and job profile |  |  |  | 2020-07-15 | 7
| Onboarding of Enterprise sales force |  |  |  | 2020-08-01 | 30
| Team KPI submission |  |  |  | 2020-08-01 | 7
| Team KPI management approval |  |  |  | 2020-08-07 | 7
| Product Development & Pricing | On Track | Head of Strategy | 0% | 2020-06-01 | 70
| Need gap scoping & opportunity mapping |  | Saajid | 100% | 2020-07-01 | 1
| Segment specific B2C product roadmap(with proposition) plan submission |  | Saajid |  | 2020-07-02 | 3
| Product design finalization and share with Finance |  | Saajid |  | 2020-07-07 | 7
| Segment specific B2B product roadmap submission(collection/disbursement) |  | Saajid |  | 2020-07-10 | 3
| Product design finalization and share with Finance |  |  |  | 2020-07-15 | 7
| Segment specific B2B product roadmap management apporval |  | Saajid |  | 2020-07-21 | 7
| Channel Charges & Commission management submission |  |  |  | 2020-07-22 | 15
| Channel Charges & Commission management approval |  |  |  | 2020-08-07 | 5
| Merchant Charges & Commission submission |  |  |  | 2020-06-15 | 15
| Merchant Charges & Commission management approval |  |  |  | 2020-08-07 | 7
| Product configuration in the System |  |  |  |  | 0
| Customer Charges/ Pricing configuration in the System |  |  |  |  | 0
| Channel Charges & Commission configuration in the System |  |  |  |  | 0
| Agreement review, renewal & contract sign | On Track | Ziaur | 20% | 2020-06-01 | 122
| Prepare list of existing contracts & prioritize the criticality |  | Rezwanul | 100% | 2020-06-01 | 7
| kick off renewal & new contract negotiation process |  | Rezwanul | 100% | 2020-06-07 | 7
| USSD agreement review/renewal with GP, Robi & banglalink |  | Saajid | 100% | 2020-10-01 | 0
| USSD agreement signing with Teletalk |  | Saajid |  | 2020-08-07 | 55
| USSD connectivity establishment with Teletalk |  | Saajid |  | 2020-10-01 | 0
| SMS agreement review/renewal with GP, Robi & banglalink |  | Saajid |  | 2020-07-15 | 78
| SMS connectivity establishment with Teletalk |  | Saajid |  | 2020-09-25 | 5
| Top-up Agreement with all |  | Saajid |  | 2020-06-01 | 122
| Top-up Connecivity with all |  | Saajid |  | 2020-06-25 | 98
| Agreement with EC- NID Server |  | Akram |  | 2020-07-20 | 73
| Connectivity with EC- NID Server |  | Akram |  | 2020-07-30 | 63
| Agrement with payment vendors: Visa, Master, UnionPay |  | Mani |  | 2020-07-01 | 92
| Integration with Visa, Master, Union Pay, Amex |  | Manik |  | 2020-08-01 | 61
| Agreement with banks for cash management |  | Majid |  | 2020-08-01 | 61
| Brand & Market Communication | On Track | Head of Brand | 0% | 2020-07-07 | 60
| Brand development |  | Head of Brand
| Brand development workshop |  | Nuzhat | 100% | 2020-07-07 | 38
| Brand workshop presentation to management |  | Nuzhat | 100% | 2020-08-14 | 6
| Brand logo submission |  | Nuzhat | 100% | 2020-07-16 | 29
| Brand logo review & approval by management |  | Project Director |  | 2020-08-07 | 7
| Brand logo architecture & elements/ Logo guideline submission |  | Nuzhat |  | 2020-08-15 | 16
| Brand essence, value, positioning submission |  | Nuzhat |  | 2020-08-15 | 16
| Vision & Mission submission |  | Nuzhat |  | 2020-08-15 | 16
| Brand imagery, layout, look and fill, Tone of voice |  | Nuzhat |  | 2020-09-01 | 14
| Visual guideline submission |  | Nuzhat |  | 2020-09-01 | 14
| Brand guideline 1st draft submission |  | Nuzhat |  | 2020-09-01 | 14
| Brand guideline 1st draft review |  | Nuzhat |  | 2020-09-01 | 14
| Brand guideline final submission |  | Nuzhat |  | 2020-09-15 | 7
| Brand guideline final review and sign off |  | Project Director |  | 2020-09-22 | 8
| Brand strategic framework |  | Nuzhat |  | 2020-09-01 | 14
| Phase by phase brand development plan |  | Nuzhat |  | 2020-08-15 | 16
| Brand copyright application |  | Nuzhat |  | 2020-08-15 | 16
| Creative & Production | On Track | Head of Brand |  | 2020-08-14 | 45
| Brief sharing to creative agencies for pitch |  | Nuzhat |  | 2020-08-14 | 4
| Creative agency pitch |  | Nuzhat |  | 2020-09-01 | 9
| Creative agency shortlist and negotiation |  | Nuzhat |  | 2020-09-01 | 9
| Creative agency awarding management approval |  | Project Director |  | 2020-09-10 | 10
| Creative agency agreement signing |  | Nuzhat |  | 2020-09-20 | 10
| Creative agency on board |  | Nuzhat |  | 2020-10-01 | 6
| Media | On Track | Head of Brand |  | 2020-08-07 | 22
| Media agency brief for pitch |  | Jesan |  | 2020-08-07 | 8
| Media agency pitch |  | Jesan |  | 2020-08-14 | 8
| Media agency shortlist and negotiation |  | Jesan |  | 2020-08-14 | 9
| Media agency awarding management approval |  | Jesan |  | 2020-08-23 | 8
| Media agency agreement signing |  | Jesan |  | 2020-09-01 | 6
| Media agency on board |  | Jesan |  | 2020-09-01 | 6
| Digital marketing | On Track | Head of Digital |  | 2020-08-07 | 52
| Digital marketing agency brief for pitch |  |  |  | 2020-08-07 | 8
| Digital marketing agency pitch |  |  |  | 2020-08-14 | 8
| Digital marketing agency shortlist and negotiation |  |  |  | 2020-08-14 | 9
| Digital marketing agency awarding management approval |  |  |  | 2020-08-23 | 8
| Digital marketing agency agreement signing |  |  |  | 2020-09-01 | 6
| Digital marketing agency on board |  |  |  | 2020-09-01 | 6
| Digital Marketing Strategy & Topline plan development |  |  |  | 2020-09-07 | 7
| Digital Marketing Strategy & Topline plan apporval |  |  |  | 2020-09-14 | 16
| Soft launch Campaign brief to digital marketing agency |  |  |  | 2020-09-07 | 7
| Digital marketing plan submission for soft launch |  |  |  | 2020-09-15 | 7
| Review and approval of digital marketing plan for soft launch |  |  |  | 2020-09-15 | 7
| Work order to digital marketing agency for soft launch |  |  |  | 2020-09-22 | 8
| Soft launch execution in digital space |  |  |  | 2020-10-01 | 29
| Social networking_Facebook page launch |  |  |  | 2020-10-01 | 29
| Social networking Linkedin page launch |  |  |  | 2020-10-01 | 29
| Social networking_Twitter page launch |  |  |  | 2020-10-01 | 29
| Social networking_Instagram page launch |  |  |  | 2020-10-01 | 29
| Promotion through Social media |  |  |  | 2020-10-01 | 29
| Promotion through Google (GDN) |  |  |  | 2020-10-01 | 29
| Market Communication for Soft launch |  | Head of Brand
| Draft launch plan for soft launch submission |  |  |  | 2020-08-14 | 17
| Campaign brief to creative agency |  |  |  | 2020-08-07 | 7
| Draft campaign proposal from creative agency |  |  |  | 2020-08-14 | 17
| Trade POSM design for launch- draft submission |  |  |  | 2020-09-01 | 13
| Trade POSM design for launch- Review & mgt. approval |  |  |  | 2020-09-14 | 8
| Trade POSM design for launch- final output delivery |  |  |  | 2020-09-22 | 8
| Agent communication material design |  |  |  | 2020-04-10 | 15
| Website | On Track | Head of Brand | 0% | 2020-08-01 | 150
| Website requirement collection for stakeholder |  | Wasi | 100% | 2020-08-01 | 6
| Website requirement sign off |  | Wasi | 50% | 2020-08-07 | 5
| Meeting with potential vendors |  |  |  | 2020-08-07 | 7
| RFQ for website |  |  |  | 2020-08-14 | 17
| Proposal submission by vendors for website |  |  |  | 2020-08-14 | 17
| Budget approval for Website |  |  |  | 2020-09-01 | 6
| PO issue for website |  |  |  | 2020-09-01 | 6
| Website domain purchase |  | Tech/SCM |  | 2020-09-07 | 7
| Website hosting plan finalization |  | Tech/SCM |  | 2020-09-14 | 16
| Website english content collection and sharing with the vendor |  | Head of digital |  | 2020-09-14 | 16
| Website images/ graphic elements sharing with the vendor |  | Head of digital |  | 2020-09-14 | 16
| Website development -Beta version |  | Vendor |  | 2020-09-15 | 30
| Website on air for soft launch |  | Vendor |  | 2020-10-15 | 7
| Website security certification |  | Tech |  | 2020-09-15 | 30
| Website development - Final version |  | Vendor |  | 2020-11-01 | 45
| Website on air_Final version (commercial) |  | Vendor |  | 2020-12-16 | 15
| Internal Communication | On Track | Brand Manager |  | 2020-08-14 | 50
| Internal communication plan submission |  |  |  | 2020-08-14 | 17
| Internal communication plan approval |  |  |  | 2020-09-01 | 6
| Internal communication activity for soft launch execution |  |  |  | 2020-10-01 | 21
| Call Center Readiness | On Track | Raisul | 5% | 2020-07-15 | 60
Call Centre
| Call Center Requirement Finalization |  |  | 100% | 2020-07-15 | 9
| RFP/ RFQ For Call Center |  |  | 100% | 2020-07-25 | 13
| Technical Evaluation |  |  | 100% | 2020-08-07 | 7
| Vendor Evaluation |  |  |  | 2020-08-07 | 7
| Call Center Vendor Finalization & approval |  |  |  | 2020-08-07 | 7
| Call Center Vendor PO issue |  |  |  | 2020-08-15 | 7
| Call Center Vendor agreement signing |  |  |  | 2020-08-15 | 7
| Call Center Agent on boarding |  |  |  | 2020-09-01 | 6
| Call Center Agent Training |  |  |  | 2020-09-01 | 6
| Call centre UAT |  |  |  | 2020-09-07 | 8
| Going Live |  |  |  | 2020-09-15 | 16
| Call centre agent for retailer and merchant |  |  |  | 2020-09-15 | 16
| Digital customer service interface activation |  |  |  | 2020-09-15 | 16
KYC & Customer data management
| KYC management process submission |  |  |  | 2020-08-07 | 8
| KYC management process sign off |  |  |  | 2020-08-15 | 7
| KYC archiving vendor sourcing |  |  |  | 2020-08-07 | 8
| KYC archiving vendor negotation and management approval |  |  |  | 2020-08-15 | 7
| KYC archiving vendor PO issue |  |  |  | 2020-09-22 | 8
| KYC vendor on boarding |  |  |  | 2020-09-01 | 14
| KYC physical archiving |  |  |  | 2020-09-15 | 16
| Initiate PR & external communication | On Track |  | 0% | 2020-08-01 | 60
| RFP/ RFQ For PR Agency |  |  |  | 2020-08-10
| Review Proposal / Agency Pitch |  |  |  | 2020-08-20
| Shortlist Agency & Negotiation |  |  |  | 2020-08-20
| Management Approval |  |  |  | 2020-08-20
| PR agency agreement |  |  |  | 2020-08-20
| PR Strategy & Plan submission |  |  |  | 2020-08-20
| PR Strategy & Plan approval |  |  |  | 2020-09-16
| PR activity for kick off |  |  |  | 2020-09-16
| Top tier Electronic media visit |  |  |  | 2020-09-16
| Top tier Print media visit |  |  |  | 2020-09-16
| Top tier Online media visit |  |  |  | 2020-09-16
| CEO's interview in Electronic media |  |  |  | 2020-09-16
| CEO's interview in Print media |  |  |  | 2020-09-16
| CEO's interview in online news portal |  |  |  | 2020-09-16
| Soft Launch preparation | On Track | Project Manager | 0% | 2020-09-01 | 31 | 75
| Launch plan (list of activity finalize) |  | Project Manager |  |  |  | 0
| Launch modality finalization |  | Project Director |  | 2020-09-01 | 1 | 15
| Launch campaign plan 1st draft submission |  | Project team |  | 2020-09-10 | 5 | 3
| Launch campaign plan management review |  | Project Director |  | 2020-09-15 | 5 | 7
| Launch campaign plan finalization/ management apporval |  | Project Director |  | 2020-09-20 | 5 | 5
| Launch budget approval |  | Project Director |  | 2020-09-20 | 7 | 6
| Soft Launch |  | Project Director |  | 2020-10-01 | 1 | 7
7
This is an empty row
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | To add more data, Insert new rows ABOVE this one

## Tech By Shahab
Priority | Class | milestone |  | Responsibility | Completion | Start Date | End date | Dependancy
A |  | Technology : Technology Architecture Planning & Deployment | Med Risk | Tech Head | 10% | 2020-04-10
|  | Technology planning & system |  | Shahab | 100% | 2020-04-10
|  | Tech system detail plan and budget submission |  | Shahab | 100% | 2020-04-10 | 2020-04-25
|  | Tech system detail plan and budget approval |  | Project Director | 0% | 2020-07-15 | 2020-07-31
|  | Aggregator integration_ITCL |  | Shahab |  | 2020-10-15 | 2020-12-30
|  | Bank API Integration |  | Shahab |  | 2020-10-15 | 2020-12-30
|  | Payment Gateway API Integration |  | Shahab |  | 2020-10-15 | 2020-12-30
|  | e-Commerce Platform API Integration |  | Shahab |  | 2020-10-15 | 2020-12-30
|  | International Remittance Services API Integration |  | Shahab |  | 2020-10-15 | 2020-12-30
|  | Bill Payment Merchant API Integrations |  | Shahab |  | 2020-10-15 | 2020-12-30
|  | Value Added Service Merchant API Integration |  | Shahab |  | 2020-10-15 | 2020-12-30
|  | Integration with Google mapping |  | Shahab |  | 2020-10-15 | 2020-12-30
|  | Integration with NPSB for other banks fund transfer (Add money) |  | Tech Head |  | 2020-10-15 | 2020-12-30
|  | Recruitment requisition to HR |  | Shahab |  | 2020-04-10 | 2020-04-25
|  | Recruitment interview for tier-3 |  | Shahab |  | 2020-06-01 | 2020-06-07
|  | Final selection and appointment letter issue of tier-3 |  | Shahab |  | 2020-06-01 | 2020-06-07
|  | On boarding of tier-3 |  | Shahab |  | 2020-07-01 | 2020-07-07
|  | Recruitment interview for tier-2 |  | Shahab |  | 2020-06-01 | 2020-06-07
|  | Final selection and appointment of tier-2 |  | Shahab |  | 2020-06-01 | 2020-06-07
|  | On boarding of tier-2 |  | Shahab |  | 2020-07-01 | 2020-07-07
|  | Recruitment interview for tier-1 |  | Shahab |  | 2020-08-01 | 2020-08-15
|  | Final selection and appointment of tier-1 |  | Shahab |  | 2020-08-16 | 2020-08-31
|  | On boarding of tier-1 |  | Shahab |  | 2020-10-01 | 2020-10-31
|  | Team KPI submission |  | Shahab |  | 2020-08-01 | 2020-08-31
|  | Team KPI management approval |  | PD |  | 2020-09-01 | 2020-09-30
|  | DFS Platform Development | On Track | Tech Head | 20% | 2020-06-01
|  | DFS platform requirment compilation - SRS |  | Manik | 0% | 2020-06-23 | 2020-02-28
|  | Functional Business requirement collection from relevant stakeholders |  | Business | 0% | 2020-06-24 | 2020-06-05
|  | Functional Business requirement draft submission |  | Business | 0% | 2020-07-05 | 2020-06-15
|  | Functional Business requirement signoff |  | Project director | 0% | 2020-07-12 | 2020-06-15
|  | Prepare SRS (Software requirement Specification) |  | Manik/Business Team |  | 2020-07-15 | 2020-06-30
|  | SRS signoff |  | Project Director |  | 2020-07-25 | 2020-06-30
|  | Detail project roadmap submission |  | Shahab |  | 2020-07-30 | 2020-06-30
|  | Hardware & associated 5 yrs infra installation |  | Shahab |  | 2020-08-01 | 2020-08-31
|  | DR site & Replica installation |  | Shahab |  | 2020-11-01 | 2020-11-30
|  | MNO connectivity establishment |  | Shahab |  | 2020-09-01 | 2020-09-30
|  | 3rd party integration |  | Shahab |  | 2020-09-01 | 2020-09-30
|  | Existing data migration |  | Shahab |  | 2020-09-01 | 2020-09-30
|  | Phase-1 deployment activity finish |  | Shahab |  | 2020-10-01 | 2020-10-15
|  | Phase-1 UAT |  | Shahab |  | 2020-10-01 | 2020-10-31
|  | Phase-1Testing& Bug fixing |  | Shahab |  | 2020-10-01 | 2020-10-31
|  | Platform handover to DFS team |  | Shahab |  | 2020-10-15 | 2020-10-31
|  | Platform live with phase-1 requirment |  | Shahab |  | 2020-10-15 | 2020-10-31
|  | Application Platform Architecture Design Plan |  | Tech Head
|  | (1) Customer App Workshop |  | Business
|  | Customer app requirement compilation |  | Business
|  | Customer app requirement finalization (functional & UI UX) & Signoff |  | PD
|  | Customer app development RFQ float with the vendors |  | Akram
|  | Customer app, Vendor proposal submission |  | Akram
|  | Technical evaluation of vendors and short listing |  | Project team
|  | Commercial negotiation with vendor |  | Akram
|  | Customer app vendor management approval |  | Project Director
|  | Customer app vendor PO issue |  | Akram
|  | Customer app development kick off |  | Shahab
|  | Customer app UI/UX development and management review |  | Shahab
|  | Customer app final UI/UX development and management approval |  | PD
|  | Customer app Beta release |  | Shahab
|  | Customer app UAT |  | Shahab
|  | Customer app bug fixing |  | Shahab
|  | App Terms & Conditions development |  | Business
|  | App Terms & Conditions legal vetting |  | Business
|  | Customer app final release in app store (Android version) |  | Project team
|  | Customer app final release in app store (iOS version) |  | Shahab
|  | (2) Agent app Project team formation & Charter signoff |  | Business
|  | Agent app requirement compilation |  | Business
|  | Agent app requirement finalization (functional & UI UX) & Signoff |  | PD
(2) Agent app development RFQ float with the vendors
Agent app, Vendor proposal submission
Technical evaluation of vendors and short listing
Commercial negotiation with vendor
Agent app vendor management approval
Agent app vendor PO issue
|  | Agent app development kick off |  | Shahab
|  | Agent app UI/UX development and management review |  | Shahab
|  | Agent app final UI/UX development and management approval |  | Shahab
|  | Agent app bug fixing |  | Shahab
|  | Agent app Beta release |  | Shahab
|  | Agent app UAT |  | Shahab
|  | Agent app final release in app store (Android version) |  | Shahab
|  | (3) DSO app project team formation and project charter signoff |  | PD
DSO App Requirement Compilation
|  | DSO app requirement finalization (functional SRS & UI/UX) & Signoff |  | PD
|  | Distribution management system (DMS) development |  | Tech Head
|  | Distribution management system (DMS) live |  | Tech Head
DSO app development RFQ float with the vendors
DSO app, Vendor proposal submission
Technical evaluation of vendors and short listing
Commercial negotiation with vendor
DSO app vendor management approval
DSO app vendor PO issue
|  | DSO app SRS UI/UX development and management review |  | PD
|  | DSO app SRS final UI/UX development and management approval |  | PD
|  | DSO app development kick off |  | Shahab
|  | DSO app bug fixing |  | Shahab
|  | DSO app Beta release |  | Shahab
|  | DSO app UAT |  | Shahab
|  | DSO app final release in app store (Android version) |  | Shahab
(4) Merchant app requirement compilation
|  | Merchant app requirement finalization (functional SRS & UI/UX) & Signoff |  | PD
Merchant app development RFQ float with the vendors
Merchant app, Vendor proposal submission
Technical evaluation of vendors and short listing
Commercial negotiation with vendor
Merchant app vendor management approval
Merchant app vendor PO issue
Merchant app SRS UI/UX development and management review
Merchant app SRS final UI/UX development and management approval
Merchant app development kick off
Merchant app bug fixing
Merchant app Beta release
Merchant app UAT
Merchant app final release in app store (Android version)
|  | ERP & HRM Deployment | On Track | Tech Head | 0% | 2020-06-15 |  |  | SCM/HR/Payrol
|  | ERP solution development |  | Tech Head |  | 2020-07-15 | 2020-08-15
|  | ERP Implementation |  | Tech Head |  | 2020-07-15 | 2020-09-30
|  | HR management system development |  | Tech Head |  | 2020-07-15 | 2020-08-15
|  | HR management system go live |  | Tech Head |  | 2020-07-15 | 2020-09-30
|  | Payroll software development |  | Tech Head |  | 2020-07-15 | 2020-08-15
|  | Payroll software go live |  | Tech Head |  | 2020-07-15 | 2020-09-30
|  | IT Infrastructure & Support | On Track | Tech Head | 0% | 2020-07-01
|  | Physical server requirement finalization & vendor sourcing |  | Akram | 100% | 2020-06-28 | 2020-09-30
|  | Physical server purchase PO |  | Akram | 0% | 2020-07-01 | 2020-10-31
|  | Immediate Server Purchase (Low Profile) |  | Akram | 0% | 2020-06-24
|  | Immediate Server Purchase (High Profile) |  | Akram | 0% | 2020-06-30
|  | DFS network device purchase PO (Router, Switch, Firewall) |  | Akram | 0% | 2020-07-01
|  | Hardware and software requirement compilation (employee & business) (Laptop) |  | Full Team | 0% | 2020-07-01
|  | Hardware vendor negotiation and management approval |  | Akram | 0% | 2020-07-01
|  | Hardware delivery by vendor - low profile server |  | Akram | 0% | 2020-07-23
|  | Technical Compliance Framework Requirements | On Track | Tech Head | 0% | 2021-01-01
|  | Cyber security risk assesment report submission |  | Tech Head |  | 2021-01-01 | 2021-01-31
|  | ISO 27001certification |  | Tech Head |  | 2021-01-01 | 2021-01-31
|  | PCI-DSS certification |  | Tech Head |  | 2021-01-01 | 2021-01-31
|  | PA-DSS |  | Tech Head |  | 2021-01-01 | 2021-01-31
|  | Application Security Testing |  | Tech Head |  | 2021-01-01 | 2021-01-31
|  | VA/PT Testing |  | Tech Head |  | 2021-01-01 | 2021-01-31
|  | Back-office Network Requirements |  |  | 0% | 2020-09-01
|  | Domain access setup project |  |  | 0% | 2020-09-01
|  | Unified Communication (UC) Solution Proposal (Office 365 / Exchange) |  |  | 0% | 2020-09-01
|  | Enterprise Instant Messaging Project |  |  | 0% | 2020-09-01
|  | Web-based collaborative platform solution proposal and Project Plan |  |  | 0% | 2020-08-01
|  | Patch Management Project |  |  | 0% | 2020-09-01
|  | Infrastructure Monitoring Project |  |  | 0% | 2020-08-01
|  | IT device management solution |  |  | 0% | 2020-09-01
|  | NTP Server configuration project for DFS |  |  | 0% | 2020-09-01
|  | Server Backup and Recovery Solution Project |  |  | 0% | 2020-10-01
|  | File Server configue for Users of DFS. |  |  | 0% | 2020-09-01
|  | Asset TAG: Purchase Device from Amazon.co.uk (Dymo Label Writer) |  |  |  | 2020-09-01
|  | Assign IT Asset TAG |  |  | 0% | 2020-09-01
|  | Firewall Policy create for DFS |  |  | 0%
|  | SDN design and Deployment planning. |  |  | 0%
|  | Manpower HeadCount wise PC Requirement |  |  | 0%
|  | Office networking plan & budget approval |  | PD | 0% | 2020-07-01 | 2020-07-15
|  | Office networking vendor sourcing |  | Akram | 0% | 2020-07-15 | 2020-07-31
|  | Office networking vendor negotation and management approval |  | Akram | 0% | 2020-08-07 | 2020-08-14
|  | Office networking vendor PO issue |  | Akram | 0% | 2020-08-01 | 2020-08-07
|  | Office networking implementation by vendor(s) |  | Shahab | 0% | 2020-08-07 | 2020-08-14
|  | Metronet Colocation Setup |  |  | 0%
|  | Colocation requirement finalization |  |  | 0%
|  | Buy Public IP /25 for DFS |  |  | 0%
|  | 42U Rack |  |  | 0%
|  | 8 Port PDU *2 |  |  | 0%
|  | Colocation quote collection - Single Vendor -> Metronet |  |  | 0%
|  | Ordered Device Implementation @ Metronet |  |  | 0%
|  | Router |  |  | 0%
|  | Switch |  |  | 0%
|  | Firewall |  |  | 0%
0%
|  | UCASH Network & Server Installation Assessment |  |  | 0%
|  | Infrastructure Network Architecture Design |  |  | 0%
|  | MAP All I/O |  |  | 0%
|  | Map all channels I/O |  |  | 0%
|  | Map All VM's Credentials |  |  | 0%
|  | Map All Router Credentials & Configurations |  |  | 0%
|  | Map All Switch Credentials & Configurations |  |  | 0%
|  | Map Firewall Configuraiton Passthrough |  |  | 0%
|  | Map All Physical Server Configurations |  |  | 0%
|  | User's Access Level |  |  | 0%
|  | Application Level |  |  | 0%
|  | DB Level |  |  | 0%
0%
|  | Policy Framework Establishment |  |  | 0%
|  | Device policy submission |  |  | 0%
|  | Device policy management approval |  |  | 0%
|  | Internet access policy submission |  |  | 0%
|  | Internet access policy management approval |  |  | 0%
|  | Policy for VPN Connection with SPP |  |  | 0%
0%
|  | Cyber Security Planning & Implementation (NOC Commissioning) |  |  | 0%
|  | Cyber Security Automation Plan Submission |  | Shahab | 0% | 2020-07-01
|  | Cyber Security Automation Plan Approval |  | PD | 0% | 2020-07-10
|  | NOC Design & Setup |  | Shahab | 0%
|  | NOC Monitor Mount area for 8 monitors |  |  | 0% | 2021-01-01
|  | Purchase Desktop for Monitoring Server Health |  | Shahab | 0% | 2020-07-10
|  | Setup heart beat monitor |  |  | 0% | 2020-07-10
|  | Setup Bandwidth Consumption Monitor |  |  | 0% | 2020-07-10
|  | Digital Forensic - Setup with Open Source & Licensed tool |  |  | 0%
0%
|  | BI Analytics & Data Warehousing Vendor Sourcing |  |  | 0%
|  | BI & Data warehouse vendor sourcing |  | Tech Head | 0% | 2021-06-01 | 2020-05-31
|  | BI & Data warehouse hardware requirement finalization |  |  | 0% | 2021-06-01
|  | BI & Data warehouse PO |  | Tech Head | 0% | 2021-06-01 | 2021-05-31
|  | New Floor Setup Requirements |  |  | 0% | 2021-06-01
|  | Device Required |  |  | 0%
|  | Wireless for new SSID - Linksys EA9500 *16 |  |  | 0%
|  | 26U Rack |  |  | 0%
|  | Mikrotik CCR1072-1G-8S+ *2 |  |  | 0%
|  | IP Phone (GrandStream GXP1625) * 24 |  |  | 0%
|  | 3KV KSTAR UPS for Rack Equipment |  |  | 0%
|  | HP Prodesk 600 G4 for IP Telephony (i7, 16GB, 1TB) |  |  | 0%
|  | 32 Port IP NVR *2 |  |  | 0%
|  | 2MP IP Camera *24 |  |  | 0%
|  | Cisco 48Port Switch WS-C3650-48TS *4 |  |  | 0%
|  | WS-C3650-12X48FD *2 |  |  | 0%
|  | Panduit Cat-7A RJ45 Copper Cable 1000MHz or 1200MHz |  |  | 0%
|  | Panduit Dual Cat7A Faceplate (as per manpower headcount) |  |  | 0%
|  | Dual 3PIN Flat Power Outlet per Desk |  |  | 0%
|  | Internet Connection - 100mpbs full duplex |  |  | 0%

## Tech roadmap
| September | October |  |  |  | November |  |  |  | December
| 4W | 1W | 2W | 3W | 4W | 1W | 2W | 3W | 4W | 1W | 2W | 3W | 4W
1. Core DFS System | September 4W: 100%
2. Distributor | September 4W: 100%
Agent On Boarding - Back Office
Agent On Boarding - DSO App
Dashboard View
Demarcation Management
DSO Profile Creation
DSO Route Assign
Duty Shifting & Roastering
eMoney Refund - Agent to DSO
eMoney Refund - DSO to Distributor
eMoney Transfer - Distributor to DSO
eMoney Transfer - DSO to Agent
Exit Process
Lifting
Login
On-Boarding
QA
Refund
Route Creation
Route Modify
3. DSO APP & Activity | September 4W: 100%
Agent /Merchant on boarding through e-KYC process API
All Notification Platform
Cash requisition to Distribution House
Cash Send & Receive to Agent
E-money requisition to Distribution House
E-money Send & Receive to Agent
error and warning message
Individual Route wise dash board
Localization
QA
Login
4. Agent App | September 4W: 50%; October 1W: 80%; October 2W: 100%
Cash In
Cash Receive from DSO
Cash Request to DSO
Customer On Boarding (eKYC/pKYC)
Customer On Boarding (eKYC/pKYC) UI & API integration
Dashboard View
DMP Payment | bar: October 2W
E-money Receive from DSO | bar: October 2W
E-money request to DSO | bar: October 2W
error and warning message | bar: October 2W
IVAC Payment | bar: October 2W
Localization | bar: October 1W
Login | bar: October 1W
Notification | bar: October 1W
PIN Reset | bar: October 1W
PIN Setting | bar: October 1W
QA | bar: October 1W to October 2W
5. Ucash Migration | September 4W: 100%
6. Upay Migration | September 4W: 10%; October 1W: 20%; October 2W: 100%
7. USSD | September 4W: 100%
8. Customer App | October 1W: 10%
Self Registration | bar: September 4W to October 1W
TOP up | bar: September 4W to October 1W
Send Money | bar: September 4W to October 1W
Log In | bar: September 4W to October 2W
Cash In (Agent) | bar: September 4W to October 2W
Cash Out (Agent) | bar: September 4W to October 2W
DMP Payment | bar: October 3W
DPDC Payment | bar: October 3W
Bank Tagging | bar: September 4W to October 4W
Card Tagging | bar: September 4W to October 4W
Payment (Merchant) | bar: September 4W to October 4W
Agent Banking Tagging | bar: November 1W
Cash Out (UCB) | bar: September 4W to November 2W
Bank | bar: September 4W to November 2W
Card | bar: September 4W to November 2W
ATM | bar: September 4W to November 2W
Cash Out other bank | bar: November 3W
Remittance | bar: November 3W
In App Payment | bar: November 3W
Digital Payment | bar: September 4W to November 4W
Integration | bar: September 4W to November 4W
9. Merchant App | October 1W: 10%
Payment Receive | bar: October 2W
Log In | bar: October 2W
QR (EMVCo) | bar: October 2W
Settlement | bar: October 3W
Dispute Management | bar: October 3W
Cash Back | bar: October 3W
Payment History | bar: October 4W
Pin Reset | bar: October 4W
Dynamic QR | bar: October 4W
QA | bar: November 1W
Deliver For UAT | bar: November 2W
Pin set by IVR | bar: December 3W to December 4W

## Team
[5 empty] | 2020-06-01 | Jul | Aug | Sep | Oct | 2020-11-01
milestone | Status | Ground Activity | Start | End
Robi Brand | Live | 60 HSC crash courses | 2018-04-01 | 2018-05-31
| Live | 16 Master Classes | 2018-04-01 | 2018-05-31
| live | Chess Master National Tournament | 2018-04-10 | 2018-05-10
| Live | Customized network strength comparisons | 2018-04-01 | 2018-05-20
| Live | Divisional Unique TVC engagement videos | 2018-04-21 | 2018-05-31
| Live | 64 Unique TVCs | 2018-04-01 | 2018-04-22
AT Brand | Live | YOLO Adda (Youth Hangout Spot) | 2018-04-05 | 2018-05-06
| Live | YOLO Fest ( Campus base Activation with Concert) | 2018-04-10 | 2018-05-10
| Live | 4G Campus tour | 2018-04-24 | 2018-06-06
| Live | Central, Eastern auto wheel sales drive | 2018-04-01 | 2018-04-30
Media & Communication (Robi-AT) |  | Airtel Best 4G Network (TV, Digital, FM, Cinema) | 2018-04-27 | 2018-05-31
|  | Airtel Acquisition_My First Airtel (TV, Digital, FM) | 2018-06-01 | 2018-07-04
| Live | Robi Unique TVC (TV, Digital, FM, Cinema, Print) | 2018-04-03 | 2018-04-25
| Live | Robi 4G Data Offer, 1GB/d TK 199 | 2018-04-10 | 2018-05-10
| Delay | Robi Device, Huawei 4G Handset (TV, Digital) | 2018-04-10 | 2018-04-20
| Delay | 4G Product Offer # 4.5 Pre Paid Acq. (TV, Digital, FM, Cinema) | 2018-04-25 | 2018-05-10
|  | Ramadan Thematic Noor App Launch (TV, Digital, FM, Cinema) | 2018-05-11 | 2018-06-14
|  | Noor Product (TV, Digital, FM, Cinema) | 2018-05-17 | 2018-06-14
|  | Eid Delight (TV, Digital, FM, Cinema) | 2018-06-01 | 2018-06-14
|  | 4G Product Offer # FIFA (Digital, *TV*) | 2018-06-10 | 2018-06-30
|  | Youtube One (Digital Only) | 2018-04-22 | 2018-05-20
|  | Data Carry Forward (Digital Only) | 2018-05-15 | 2018-06-30
| Live | Iflix (Digital Only) | 2018-04-10 | 2018-06-30
| Live | My Sports (Digital Only) | 2018-04-08 | 2018-05-28
|  | OTT Platform (Digital Only) | 2018-04-22 | 2018-06-30
| Live | Brand Engagement (Digital Only) | 2018-04-04 | 2018-06-30
|  | HVC Family Pack (Digital Only) | 2018-04-20 | 2018-06-30
| Live | Boishakhi Offer (Digital Only) | 2018-04-10 | 2018-04-20
|  | Pre - Ramadan Delight (Digital Only) | 2018-04-22 | 2018-06-08
|  | Jhotpot Revamp (Digital Only) | 2018-06-08 | 2018-06-30
|  | Voice Bundle (Digital Only) | 2018-05-08 | 2018-05-20
| Live | Gifting (Digital Only) | 2018-04-15 | 2018-04-25
|  | Handset Bundle (Digital Only) | 2018-05-08 | 2018-06-15
| Live | CLM (Bangla New Year , Handset, Ramadan, Post Eid, Winback , FIFA, Dhonnobad (Digital Only) | 2018-04-06 | 2018-06-30
| Delay | CE : My Robi App (Digital Only) | 2018-04-10 | 2018-06-30
|  | CE : Segmented (Digital Only) | 2018-05-01 | 2018-05-31
Subsidery Company formation | Done | Board resolution for DFS subsidiary formation
| Done | Subsidiary Company Formation
Bangladesh Bank approval for license
| Done | Trade License
| Done | eTIN Certificate
| Done | VAT Registration Certificate
Copy Right Certificate
| Done | Organogram Approval by Board/management
| Done | New Company Bank Account Creation

## Top line status (hidden)
UCB DFS Project
Project Lead : Sydul H Khandaker
2020-05-01
Key critical milestone for soft-launch | Start Date | End date | % | Key task pending | Responsibility
Subsidiary Company Formation |  |  | 50 | Bangladesh Bank Approval for DFS license, WIP | Company secretary
Business Strategy & Plan Sign-off
Critical resource onboarding |  |  |  | WIP, Head of PR & external communication onboarding WIP, | A Pasha
Business Process define & Sign-off | 2020-07-01 | 2020-07-30 |  | Team to complete 13 existing process define and get approval by 29th of July 20 | Project team
Key Service & Hardware Procurement & WH buildup |  |  |  | Final Hardware BoQ submission & get approval for purchase by 23 Jul20 | Shahab
Tech Readiness : DFS Platform development
Ucash, Upay data sanitization & migration to new platform |  |  |  | Data extracted, mapping with Upay WIP,
Apps development : Customer, Agent, DSO, Merchant |  |  |  | SRS Finalization WIP
NOC Commissioning
Integration (EC Server, UCB-CBS & CMS, Payment Gateways, MNOs)
Onboarding of distributor, Agent Merchant, B2B, G2B |  |  |  | Team to finalize the strategy & target by this wk
Channel Commissioning
Product & pricing finalization |  |  | 70
Review, renewal, discontinuation of existing & new contract |  |  | 20
Brand & Logo finalization
Website Development
Call Center Readiness
KYC Management
Initiate PR & Communication
Soft Launch Preparation
Subsidiary company formation & BB approval | 2020-06-01 | 2020-08-10 |  | Bangladesh Bank approval along with PSO/ PSP license | Company secretary
Business strategy & plan sign-off | 2020-06-15 | 2020-08-10 |  | Business strategy & plan board approval | Ziaur
Business Process define & Sign-off | 2020-07-01 | 2020-08-10 |  | 13 business process signed off | Project
Critical resource onboarding | 2020-06-07 | 2020-08-07 |  |  | Pasha
Existing resource reallocation | 2020-07-01 | 2020-08-10 |  |  | Pasha
Budget approval (Soft launch) | 2020-07-01 | 2020-08-15 |  |  | PD
Key Service & Hardware Procurement & WH buildup | 2020-07-01 | 2020-09-15 |  |  | Akram
DFS core platform readiness | 2020-07-15 | 2020-09-15 |  |  | Shahab
Ucash, Upay data sanitization & migration to new platform | 2020-07-15 | 2020-10-15 |  |  | Shahab
Apps development(Customer, Agent, DSO, Merchant) | 2020-08-15 | 2020-10-01 |  |  | Shahab
Core hardware purchase & NOC commissioning | 2020-08-15 | 2020-09-15 |  |  | Shahab
Integration (MNO, NID Server, UCB-CBS & CMS, Payments gateway | 2020-08-01 | 2020-10-10 |  |  | Shahab
ERP and HRM solution readiness | 2020-08-10 | 2020-10-10 |  |  | Shahab
Sales force tracking software | 2020-08-15 | 2020-10-10 |  |  | Shahab
Basic reporting module readiness | 2020-08-15 | 2020-09-15 |  |  | Shahab
Channel commission structure finalization | 2020-08-01 | 2020-09-15 |  |  | Biplab
Onboarding of distributor, Agent Merchant, B2B, G2B | 2020-08-21 | 2020-10-15 |  |  | Biplab
Activate B2B/B2G team | 2020-08-10 | 2020-09-30
Merchant acquisition kick off | 2020-08-15 | 2020-09-30 |  |  | Ziaur
Product & pricing finalization | 2020-08-10 | 2020-09-30 |  |  | Ziaur
Review, renewal, discontinuation of existing & new contract | 2020-06-10 | 2020-10-15 |  |  | Ziaur
All MNO (USSD & Top up) agreement renewal | 2020-07-15 | 2020-09-15 |  |  | Ziaur
Major govt. utility agreements | 2020-08-15 | 2020-10-15 |  |  | Zahid
Add money agreement with 15 banks | 2020-07-15 | 2020-11-15 |  |  | Manik
Bank agreement for lifting & refund | 2020-08-15 | 2020-09-30 |  |  | Siddiquee
New Brand name, Logo finalization & registration | 2020-07-15 | 2020-09-30 |  |  | Jesan
Creative agency onboarding | 2020-08-15 | 2020-09-21 |  |  | Jesan
Digital agency onboarding | 2020-08-15 | 2020-09-21 |  |  | Jesan
Website Development | 2020-08-01 | 2020-09-30 |  |  | Jesan
PoSM design for agents & merchants | 2020-08-01 | 2020-09-15 |  |  | Jesan
PoSM vendor selection & printing | 2020-08-10 | 2020-09-30 |  |  | Jesan
Call Center readiness & Go Live | 2020-07-20 | 2020-10-01 |  |  | Jesan
Existing customer data validation thru KYC management vendor | 2020-08-01 | 2020-10-15 |  |  | Jesan
Existing Upay & Ucash customer communication | 2020-08-01 | 2020-10-15 |  |  | Jesan
Readiness of compliance, fraud reporting and awareness | 2020-08-20 | 2020-10-30 |  |  | to be onboard
Initiate PR & external communication | 2020-08-15 | 2020-10-01 |  |  | to be onboard
Launch check list ready | 2020-09-15 | 2020-09-25 |  |  | to be prepare
Soft Launch –Go Live | to be disclosed